## Deadlines
Date | Item | Complete
2016-09-01 | Event locations and dates
2016-09-01 | Confirm # of field perimeters in use for season
2016-09-01 | Plan for consent & release forms
2016-09-15 | Any final changes for additional play fee ($500 or $1000)
2016-09-30 | Nomination of Sr. VC ***sept 15th
2016-09-30 | Nomination of SR JA ***sept 15th
2016-09-30 | Nomination of SR Head Ref
2016-09-30 | Nomination of SR LRI
2016-09-30 | Nomination of event VC's
2016-09-30 | Nomination of event JA's
2016-09-30 | Nomination of event LRI's
2016-09-30 | Nomination of FTA's & who is lead FTA
2016-10-30 | Program book coordinator for district champ book, quantity, shipping info
2016-11-01 | Finalize # of key volunteers to be trained at HQ and who they are
2016-11-01 | Dean's List Award Judge Manager
2016-11-01 | Finalize DLA interview process
2016-11-01 | Provide shipping address and contact info for carpet shipment
2016-11-15 | Additional Event registration method (waitlist or 1st come first serve)
2016-11-15 | FMS and Game specific road cases - back at HQ post the off season
2016-12-01 | deadline to add an event; this would be in instances of unexpected team growth
2016-12-12 | Volunteer of the year award - name to HQ
2016-01-04 | Public Schedules due for all events
1 week post kick off | All kick off kits are due back at HQ
2016-01-10 | Provide shipping address & contact info for additional shipments during season; if possible, the event venues
2016-01-10 | FMS Shipping address
2016-01-10 | Shipment address for awards, game specifics & other items pre season
2016-01-10 | Provide name(s) to have access to box for event management
District Champ. Program book deadlines
2016-05-15 | Spare parts back to HQ
2016-06-30 | District year end report
? | Certificate of Insurance is due each year based on your insurance renewal date

## Event Data
Event Data Sheet
Variable | Value
EventName | TBD | Fill in values here to have them propagate through the document
EventStartDate | 2025-03-08
EventYear | 2025
EventElectrical | TBD
EventAV | TBD
EventLead | TBD
EventLeadAssist | TBD
EventManager | TBD
EventVC | TBD
EventFTA | TBD

## Task List - New
Task | Responsibility | Due Date | Completed | Reference Link | Event Specific Information | Comments
EVENT DETAILS
Confirm Event dates
Venue Shipping Information
Fork Lift Booked
Floor Covering Confirmed
Machine Shop (Venue or FIRST to be identified)
Event Carpet Team Confirmed
Load-in Map
Load In Schedule Confirmed
Complete Set up Specifications Sheet
Is a Chair/Table Supplier Required?
FIRST Truck Arrival Time to Venue
FIRST Truck Departure Time from Venue
Pit Map Created
Floor Plan / Venue Layout Created
Floor Plan / Venue Layout Approved by AV
Floor Plan / Venue Layout Approved by FTA
Request for Additional Required Rooms
Event Office
Judge Deliberation Room
Judging Interview Room - FIRST Impact Award
Judging Interview Room - Dean's List Award
Quiet Room
Multi-Faith Prayer Room
Volunteer Lounge
All Gender Restroom
Breastfeeding Room
Final Confirmation of Rooms
Safety Review
Insurance Certificate
Cable Covers / Wheelchair Cable Covers
Emergency Document
Establish Planning Committee
EMT
Security
Confirm Contact Information
Regular Meetings Occurring
Reflection/Feedback Meeting
AV
Venue Walkthrough (AV & Electical Company)
Request Venue/Sponsorship Videos
Update Google Drive Folder with Revised Videos
CATERING
Initial Catering Meeting (obtain menu samples/pricing)
Review Menu with Jaeleen
Finalize Menu with Catering Company
Retreive all Dietary Restrictions | Volunteer Coordinator
Send final Numbers & Dietary Restrictions
Catering Numbers, Dietary Restrictions & Times Confirmed
TEAM COMMUNICATIONS
Press/Media Releases
Land Acknowledgement
Team Communications #1
Media invites
Prepare Venue Communications Plan
Prepare Social Media Plan (handles, hashtags, etc.)
Team Communication #2 (including carpet removal)
Script
Team Communication #3
MEDIA/MARKETING
T-Shirts
Program Book
Team Social (optional)
Invite Guest Speakers
Confirm Guest Speakers
Invite VIPs (optional)
VIP List Confirmed
VOLUNTEERS
Volunteer Coordinator (VC) Confirmed |  | October
VC introduced to Planning Committee & FIRST Event Lead |  | November
Volunteer Information Package is compeleted | VC/FIRST | Early February
Volunteer Information Package is shared with volunteers | Volunteer Coordinator | Mid-February
Volunteer Welcome Meeting |  | Monday before the event
Volunteer Trainings Sent to Volunteers |  | 2 weeks before event |  | See VC Box for details for each role
Emcee/Game Announcer Training |  |  |  | Emcee/GA Training
Safety Manager Training | Volunteer Coordinator |  |  | Safety Manager Training (requires certification too)
Lead Queuer Training | Volunteer Coordinator |  |  | Lead Queuer Training (requires certification too)
Pit Administration Superisor Training | Volunteer Coordinator |  |  | Pit Administration Supervisor Training
Volunteers for FIRST Truck Load-in / Pre-event setup | Volunteer Coordinator | 2 weeks before event
EQUITY, DIVERSITY & INCLUSION
Accessibility Survey Created |  | December
Accessibility Survey Added to Team Communication |  | December
Accessibility Survey Added to Volunteer Information Package |  | December
Accessibility Ambassador Identified |  | February
EDI CheckList
Notable AV Aspects |  | February
ACTIVATIONS
Venue booths (optional)
FIRST Swag Location
Invite FLL Explore teams to showcase (optional)
Invite FLL Challenge teams to showcase (optional)
Invite FTC teams to showcase (optional)
Confirm FIRST LEGO League Explore (optional)
Confirm FIRST LEGO League Challenge (optional)
Confirm FIRST Tech Challenge (optional)

## Detailed Schedule
#NAME? |  |  |  |  | Start Date: | 2025-03-08
Date | Day | TIME | Notes | # Vol's required | Food Count | Details
2025-03-07 | -1
|  | 13:00 | FIRST Staff Arrives - only key staff for pre-setup purposes
|  | 14:00 | Taping the floor for pit locations, identifying practice field locations. and having pit drawing available for Electric Contractors - Large measuring tape, chalkline, white tape (gaffers tape), marker
|  | 14:00 | Carpet Arrives
|  | 14:00 | Bleachers in place
|  | 15:00 | Carpet arrive by independent truck - (Volunteers to help with Carpet - any forklift requirements?)
|  | 17:00 | FIRST 53" transport truck arrives
|  | 18:00 | Dinner - field side
|  | 18:30 | AV Contractors Arrives
Arrange tables and chairs in pits as soon as pit markings are complete.
Set-up will continue until 7:00 p.m. or 8:00 p.m. – PIT layouts are priority, other aspects of the venue set-up - Tables and chairs - Volunteer Lounge to be ready - Judge Room (to be ready before 6:00 pm Day 0) *does JA want dinner - Main Gym (tables/chairs can be kept just on the right side bleachers after ram board is laid out)
By end of the evening, pits fully ready, carpet rolled out, road cases in the right areas
SECURITY | 9:00 PM- 7:00 AM | 21:00 | Leave building unless key role personnel are in attendance Security to monitor field and pits Security: 9:00 pm-7:00 am
2025-03-08 | 0 | Time | Activity
|  | 7:00 | FIRST and venue representatives arrive
|  | 7:00 | EM Arrives - Breakfast in the Student Lounge
|  | 8:00 | Set up crew volunteers (FTA/CSA/PITAdmin...) AV Contractors, FTA and FS crew arrives | 15
|  | 8:30 | Electric Contractors - pit and field and pit admin, electric work Will start with pits and then follow with main field
Before Electric Contractors leaves, make sure we have enough cable mats/ramps to ensure we can have them where needed. Pit electricity to be laid, cable mats, wheel chair mats to be installed *ensure to get more wheelchair cable covers
| Complete tasks that were not done on Day -1 |  | EL and EM meet and brief about the day and site walkthrough of all spaces - Field Setup and Event set up continues - Main field setup - PIT setup (PIT Admin, ensure viewing area is clear, pipe and drape is done, Machine shop area is clear, practice area is pipe and draped) - Create walkway for teams in/out of the main field + pipe and drape or extensions to divide group - Signage and directional signage - Judges rooms (FIRST Impact Room, DLA Room, Deliberation Room) Volunteers rooms and Team Eating spaces - Quiet Rooms, Prayer Rooms, Mentor Lounge - Corridor free of hazards / safety check - Load-in Area defined and clear - Go over guest speakers, Media and PR process, - Discuss unexpected guests and how we deal with that - Ensure Team eating spaces are clearly identified and marked - Ensure team seating on stands is marked - Directional signage for teams eating spaces, quiet room, machine shop, mentor lounge, interview rooms is clearly identified
|  | 11:00 | - IT personnel onsite to dicuss wifi and support FMS set up Confirm plans to shut down WIFI Date/Day at 12:00PM Day 0 until 8:00PM Day 2
|  | 12:30 | Lunch in Volunteer Lounge
Verify phone lines; Network drop on floor and event office with house
Practice Field set up
Set rooms as per - set up specs document
EM to work on scripts, check in with EL for questions
The event should be fuly ready other than practice field and main competition field and this includes all signage and directional signage to areas
|  | 14:00 | Prepare EM, LRI, 2 vol's to assist with team load in for 2:30 LRI +1 arrives by 2pm for team loadin.
|  | 14:15 | EMT Setup and Prepare
|  | 14:15 | Load-in and Registration, crews in place
|  | 14:30 | Team and Volunteer Registration and Load-in Meeting and Training
EL and EM to oversee process at all checkpoints to ensure we make changes if necessary to staffing and rotate people for dinner
|  | 14:30 | Team start to arrive Team Load-in (one hour team pit set up) - *Teams welcomed
|  | 15:00 | JA onsite, EM to check in and see if dinner planned, and judges room is set up fully
|  | 15:00 | EM to review Day 1 scripts with EL, MC. Ensure script readiness for Day 1: Opening and Closing Ensure we have Host Venue Guest speakers lined up first along with requested Opening Ceremonies Host Venue Videos EM to review public relations/press/guests on site and other information received. EM to conduct a walkthrough with MC, FIRST lead, flow of awards and picture taking
|  | 15:00 | EM to meet AV Team to ensure they have everything lined up for Sat/Sun EM to check in with FTA/FS to ensure media boxes are drawn out (for team media).
|  | 16:00 | Ensure inspectors have all arrived and would be ready in case teams want to do inspection
|  | 16:35 | Practise field, machine shop, eye glasses attendants in place
|  | 16:30 | Pits and Machine Shop - open
|  | 16:30 | Practice fields open only to robots with inspection completed
|  | 17:30 | Dinner - rotating with key roles at work positions - Volunteer Lounge
|  | 18:00 | Jugdes' Dinner
|  | 18:00 | Practice matches and/or filler lines if available only to inspected robots
|  | 20:00 | Review the overnight requirements, EM informs Key Vol of 7:30am morning Meeting Morning meeting to take place in stands. Check in with EM if all ok and Load-in for morning is good
|  | 20:45 | Machine shop and practise fields close
|  | 21:00 | Pits Close
Volunteers in the building: FTA, CSA, Inspectors, PIT Admin, Field Set up, Lead Queuer, Head Referee
Security arrives 20:45 |  | 21:00-07:00 | Security
2025-03-09 | 1
| Day 1 - Mar 4 | 6:45 | FIRST staff arrive, EM arrives Briefing with security before they leave
|  | 7:00 | Breakfast Ready - Volunteer Lounge
|  | 7:15 | If necessary - Load-in volunteers in place for late-arriving teams
|  | 7:30 | Late team load in
|  | 7:30 | Team 9782 arrives
|  | 7:30 | Morning Meeting with volunteers outside Event Office, dressing rm 6 - Key Volunteer meeting - *ensure all key attendees are present - morning meeting template Radios are ready and assigned Review Doors opening and registration volunteers and staff in place
Inspection Crew to support late team load in 5 members- and pit set up, no robot work
Ensure DJ is on site
|  | 7:55 | crews in place as doors open at 8am
Practise field, machine shop, eye glasses attendants in place
|  | 8:00 | Pits and all doors open
Practise field and machine shop open
|  | 8:15 | Safety Meeting - in the stands
|  | 8:15 | EM to remind PIt admin to display Woodie Flower T-shirt for teams to sign and pack it up into the case back at the end of the event as this goes to the next event for signing.
|  | 8:30 | Drivers Meeting on main field EM to check in with GRAB Production (AV) representatives on site. EM to remind AV to pump music when doors open! Ensure that GRAB is watching volume levels and maintaining a safe volume Review agenda, scripting, video playlist
|  | 8:30 | Field open for Measurement, Calibaration and Connection
|  | 9:15 | Practice Matches (9:30-10:45am) for only inspection completed robots
|  | 10:00 | Judges' snacks and drinks refreshed
|  | 10:45 | Guest speakers, Anthem singer and opening ceremonies readiness Lead Queuer to stage Match 1 teams to begin right after opening ceremonies Ensure announcments are made in PITS for all teams to go to opening ceremoinies Ensure PIT Admin is informed, no machining/cutting/drilling etc. during opening ceremonies
|  | 10:45 | Queuers prepare match #1 teams to be field side or on field for Opening Ceremonies
|  | 11:00 | Opening Ceremonies
|  | 11:00 | Venue/Sponsor Plaque Presentation
|  | 11:30 | Qualification Matches Begin
|  | 13:30 | Rotating lunch for volunteers - Volunteer Lounge
|  | 13:30 | Judges Lunch (from volunteer lounge) or with Volunteers?
|  | 13:30 | Alumin/Grade 12 Photo on competition field
|  | 14:30 | Qualification Matches
|  | 15:30 | Judges snacks and drinks refreshed
|  | 18:30 | Volunteer dinner
|  | 19:00 | EM/FIRST Staff to track down all WFFA past winners and nominees (to see who is in the building) EM to prep for Day 2 scripts
|  | 19:30 | EM to inform EKRL's of 7:30am morning meeting
|  | 19:45 | Practice Fields and Machine Shop Close
Security arrives 20:45 |  | 21:00-07:00 | Security
|  | 20:00 | Pits close
2025-03-10 | 2
EMT (7:00AM-8:00PM) |  | 6:45 | FC staff and EM arrive
|  | 7:00 | BREAKFAST FOR VOLUNTEERS in Vol Lounge
|  | 7:30 | Morning Meeting with volunteers - Key Volunteer meeting - *ensure all key attendees are present - morning meeting template Radios are ready and assigned Review Doors opening and registration volunteers and staff in place Ensure DJ is on site
EKRL vol meeting
|  | 7:55 | crews in place as doors open at 8am
Practise field, machine shop, eye glasses attendants in place
|  | 8:00 | Pits Open, Practise field open, Machine shop open
Field open for Measurement, Calibration and Connection Safety Meeting in stands by safety manager
|  | 8:45 | Guest speakers, Anthem singer and opening ceremonies readiness Lead Queuer to stage Match 1 teams to begin right after opening ceremonies Ensure announcments are made in PITS for all teams to go to opening ceremoinies Ensure PIT Admin is informed, no machining/cutting/drilling etc. during opening ceremonies
First Match robots to be on field prior to start of cermemonies
|  | 9:00 | Opening Ceremonies
|  | 9:30 | Qualification Matches
|  | 10:00 | Judges snacks and drinks refreshed
|  | 12:30 | Rookie plaques presented ahead of alliance selection by FSM - EM coordinate this
|  | 13:00 | Alliance Selections
|  | 13:30 | Rotating lunch for volunteers - Volunteer Lounge
Judges' Lunch
|  | 14:30 | Elimination Matches (4:30-:6:00pm)
|  | 16:00 | Machine shop closed
|  | 16:30 | Practise field closed and tear down begins
|  | 16:30 | Awards Prep for Match winners and finalists
|  | 17:30 | Awards and closing ceremonies - no power tools in pits during awards
|  | 19:30 | Pits close
|  | 19:30 | EM to ensure all teams and non takedown volunteers leave the venue
|  | 19:30 | Pizza Dinner for Tear down crew and staff - field side but hidden from Teams
|  | 20:30 | Forklift and operator onsite
TEAR DOWN
|  | 19:00 | Electric Contractors arrives to start tear down, truck loads up
|  | 19:00 | AV Truck tear down begins, loads up
|  | 20:00 | AV Truck loads up
|  | 20:30 | Electric Contractors truck loads up
|  | 21:30 | FIRST Transport loads up
|  | 22:30 | Building cleared
Formulas:
Date = G1+ [Day]

## 2025 VOLUNTEERS
Forumla driven cell, please do not change |  |  |  |  | VOLUNTEERS |  |  |  | Volunteer Management System Link
Forumla driven cell, please do not change | ADD Colour Coding for Requirements
Role | Age | FIRST Exper |  |  | Volunteer Name | Pending Volunteer | Mark VMS Assigment Confirmed (Yes) | Thur PM (input "1") | Fri AM (input "1") | Fri PM (input "1") | Sat (input "1") | Sun (input "1") | Email Address | Cell Phone # | Company
KEY VOLUNTEER ROLES | Age
Volunteer Coordinator | 21 | x |  |  | #REF! |  |  | 1 | 1 | 1 | 1 | 1
Volunteer Coordinator in Training | 21 | x
*FTA #1 - FIRST Assigns | 18, and post high school or equivalent, 21 preferred | x |  |  |  |  | Yes |  | 1 | 1 | 1 | 1
FTA #2 - FIRST Assigns (optional) | 18, and post high school or equivalent, 21 preferred | x |  |  |  |  | Yes |  | 1 | 1 | 1 | 1
FTAA | 18, and post high school or equivalent | x |  |  |  |  | Yes |  |  | 1 | 1 | 1
Field Supervisor | 18, and post high school or equivalent | x | 1 |  |  |  | Yes |  | 1 | 1 | 1 | 1
Head Referee | 23 | x |  |  |  |  | Yes |  | 1 | 1 | 1 | 1
Referee 1 | 18, and post high school or equivalent | x |  |  |  |  | Yes |  | 1 | 1 | 1 | 1
Referee 2 | 18, and post high school or equivalent | x | 1 |  |  |  | Yes |  |  | 1 | 1 | 1
Referee 3 | 18, and post high school or equivalent | x |  |  |  |  | Yes |  |  | 1 | 1 | 1
Referee 4 | 18, and post high school or equivalent | [5 empty] | Yes |  |  | 1 | 1 | 1
Referee 5 | 18, and post high school or equivalent | [5 empty] | Yes |  |  |  | 1 | 1
Official Scorer 1 | 18 preferred
Official Scorer 2 | 18 preferred
Official Scorer 3 | 18 preferred
Official Scorer 4 | 18 preferred
Official Scorer 5 | 18 preferred
Lead Robot Inspector | 21 | x |  |  |  |  | Yes |  | 1 | 1 | 1 | 1
Audio/Visual Attendant | 18
Control System Advisor | 18, and post high school or equivalent | [5 empty] | Yes |  | 1 | 1 | 1 | 1
Control System Advisor | 18, and post high school or equivalent | x |  |  |  |  | Yes |  | 1 | 1 | 1 | 1
Judge Advisor - FIRST Assigns | 23 | x |  |  |  |  | Yes |  | 1 | 1 | 1 | 1
MC - Primary | 18, and post high school or equivalent | x |  |  |  |  | Yes |  |  |  | 1 | 1
GA - Primary | 18, and post high school or equivalent | x |  |  |  |  | Yes |  |  | 1 | 1 | 1
MC/GA - Back up #1 | 18, and post high school or equivalent | x |  |  |  |  | Yes |  |  | 1 | 1 | 1
MC/GA - Back up #2 (Optional) | 18, and post high school or equivalent | x
Safety Manager #1 | 21 | [5 empty] | Yes |  |  | 1 | 1 | 1
Safety Manager #2 | 21 | x
Lead Queuer | 18, and post high school or equivalent | x | 1 |  |  |  | Yes |  |  |  | 1 | 1
Scorekeeper | 18, and post high school or equivalent | [5 empty] | Yes |  |  | 1 | 1 | 1
Pit Administration Supervisor | 21 | x | 1 |  |  |  | Yes |  | 1 | 1 | 1 | 1
Pit Admin Support | 18, and post high school or equivalent
Spare Parts | 13
Inspection Manager | 18, and post high school or equivalent
Robot Inspector 1 | 18, and post high school or equivalent | x |  |  |  |  | Yes |  |  | 1
Robot Inspector 2 | 18, and post high school or equivalent | x | 1 |  |  |  | Yes |  |  | 1 | 1 | 1
Robot Inspector 3 | 18, and post high school or equivalent | x |  |  |  |  | Yes |  |  | 1 | 1 | 1
Robot Inspector 4 | 18, and post high school or equivalent | x |  |  |  |  | Yes |  |  | 1 | 1 | 1
Robot Inspector 5 | 18, and post high school or equivalent | [5 empty] | Yes |  |  | 1 | 1 | 1
Robot Inspector 6 | 18, and post high school or equivalent | [5 empty] | Yes |  |  | 1 | 1 | 1
Machine Shop #1 | 18, and post high school or equivalent & trained | [5 empty] | Yes |  |  | 1 | 1 | 1
Machine Shop #2 | 18, and post high school or equivalent & trained | [5 empty] | Yes |  |  | 1 | 1 | 1
Photographer | 13, 18 preferred
Queuer #1 | 13, 15 preferred | [5 empty] | Yes |  |  | 1 | 1 | 1
Queuer #2 | 13, 15 preferred | [5 empty] | Yes |  |  | 1 | 1 | 1
Queuer #3 | 13, 15 preferred | [5 empty] | Yes |  |  | 1 | 1 | 1
Queuer #4 | 13, 15 preferred | [5 empty] | Yes |  |  | 1 | 1 | 1
Field Resetter #1 | 13, 15 preferred | [5 empty] | Yes |  |  |  | 1 | 1
Field Resetter #2 | 13, 15 preferred | [5 empty] | Yes |  |  |  |  | 1
Field Resetter #3 | 13, 15 preferred | [5 empty] | Yes |  |  |  | 1 | 1
Field Resetter #4 | 13, 15 preferred | [5 empty] | Yes |  |  |  | 1
Field Resetter #5 | 13, 15 preferred | [5 empty] | Yes |  |  |  | 1 | 1
Field Resetter #6 | 13, 15 preferred | [5 empty] | Yes |  |  |  | 1 | 1
Field Resetter #7 | 13, 15 preferred | [5 empty] | Yes |  |  |  | 1 | 1
Field Resetter #8 | 13, 15 preferred | [5 empty] | Yes |  |  |  | 1 | 1
Field Resetter #9 | 13, 15 preferred | [5 empty] | Yes |  |  |  | 1 | 1
Field Resetter #10 | 13, 15 preferred | [5 empty] | Yes |  |  | 1 | 1 | 1
Practice Field Attendant #1 | 18, and post high school or equivalent | [5 empty] | Yes |  |  |  | 1 | 1
Practice Field Attendant #2 | 18, and post high school or equivalent | [5 empty] | Yes |  |  |  | 1 | 1
Quiet Room Attendant 1 | 18, and post high school or equivalent | [5 empty] | Yes |  |  | 1 | 1 | 1
Quiet Room Attendant 2 | 18, and post high school or equivalent | [5 empty] | Yes |  |  | 1 | 1 | 1
Accommmodation Coordinator | 21 | [5 empty] | Yes
Load In/Out Crew #1 | 13 | [5 empty] | Yes |  | 1 |  |  | 1
Load In/Out Crew #2 | 13 | [5 empty] | Yes |  | 1
Load In/Out Crew #3 | 13 | [5 empty] | Yes |  | 1
Load In/Out Crew #4 | 13
Safety Attendant (SAT) | 13 | [5 empty] | Yes |  |  | 1 | 1
Safety Attendant (SUN) | 13 | [5 empty] | Yes |  |  | 1 |  | 1
Field Setup/Disassembly #1 | 13, 18 preferred | [7 empty] | 1
Field Setup/Disassembly #2 | 13, 18 preferred | [7 empty] | 1 |  |  | 1
Field Setup/Disassembly #3 | 13, 18 preferred | [7 empty] | 1
Field Setup/Disassembly #4 | 13, 18 preferred | [7 empty] | 1 |  |  | 1
Field Setup/Disassembly #6 | 13, 18 preferred | [7 empty] | 1 |  |  | 1
Field Setup/Disassembly #7 | 13, 18 preferred | [7 empty] | 1
Field Setup/Disassembly #8 | 13, 18 preferred | [7 empty] | 1 |  |  | 1
Field Setup/Disassembly #9 | 13, 18 preferred | [7 empty] | 1
Field Setup/Disassembly #10 | 13, 18 preferred | [7 empty] | 1
Field Setup/Disassembly #11 | 13, 18 preferred | [7 empty] | 1
Field Setup/Disassembly #12 | 13, 18 preferred | [7 empty] | 1
TOTAL FEMALE % VOLUNTEERS/JUDGE |  | 17.86% | 5 | 0 |  |  |  |  | 14 | 34 | 46 | 47
Judges below (add names from VMS to track Gender balance) |  | 0% | 0 | 28 |  |  |  |  | 0 | 28 | 28 | 28
Judge Advisor - FIRST Assigns |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge Advisor Assistant |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 1 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 2 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 3 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 4 |  |  |  | 1 | [5 empty] | 1 | 1 | 1
Judge 5 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 6 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 7 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 8 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 9 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 10 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 11 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 12 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 13 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 14 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 15 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 16 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 17 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 18 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 19 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 20 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 21 |  |  |  | 1 | [5 empty] | 1 | 1 | 1
Judge 22 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 23 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 24 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 25 |  |  |  | 1 | [5 empty] | 1 | 1 | 1
Judge 26 |  |  |  | 1 |  |  | Y |  |  | 1 | 1 | 1
Judge 27
Event Manager
x
x
x
x
x
x
x
x
x
x
x
x
x
x
x
x
x
x
x
x
|  | TOTAL | 0 | 0 | Staff/AV |  |  | 0 | 0 | 0 | 0 | 0
|  | TOTAL |  | 28 | Total Volunteers including Judges and STAFF |  |  |  | 14 | 62 | 74 | 75
|  | TOTAL |  | 0 | Total Volunteers WITHOUT Judges (incl. STAFF) |  |  |  | 14 | 34 | 46 | 47

## Contacts and Planning Committee
#NAME?
PLANNING COMMITTEE CONTACT SHEET
Role | Company (FIRST/Venue) | Name | Title | Email | Phone
FIRST Lead Contact | FIRST
FIRST FSM
Facilities Lead Contact | Venue
Volunteer Coordinators | Venue
Guest Speaker/VIPs | Venue
Catering | Venue
Social Media/PR | Venue
Program Book | Venue
Logos | Venue
Video's | Venue
Event T-Shirt | Venue
CONTACT SHEET
Role | Company | Name | Title | Email | Phone
IT | Venue
Electrical | Electric Contractors
AV | AV Contractors
SHIPPING INFORMATION
Venue Name
Event Dates
Venue Address
Venue Shipping Address
Venue Shipping Contact Name and Phone#
Venue Dock Hours
Initial Shipment: Shipping Address
Initial Shipment: Shipping Contact Name
Intial Shipment Dock Hours
Carpet Shipping Address
Event Website URL
Team Capacity & Reserve Capacity for Event
Facility Event Lead cell number during event
Truck Lift Gate required

## Food Schedule
Day | Time | Meal | Who? | VC | FIRST + AV Crew | Meal Count | Total | Vegetarian | Vegan (+gluten free) | Halal | No Beef | No Pork Nor Beef | No Dairy | No Eggs | Gluten-Free, Lactose Intolerant, Pork, Shellfish, Diabetic, Beef | No Shellfish | No Nuts | Total "Regular" Meals
2025-03-07 | 19:30 | Dinner | General |  |  | 0 | [11 empty] | 0
2025-03-08 | 8:00 | Breakfast | General |  |  | 0 | [11 empty] | 0
2025-03-08 | 12:30 | Lunch | General |  |  | 0 | [11 empty] | 0
2025-03-08 | 18:00 | Dinner | General |  |  | 0 | [11 empty] | 0
2025-03-08 | 18:00 | Dinner | Judges |  |  | 0 | [11 empty] | 0
2025-03-09 | 7:00 | Breakfast | General |  |  | 0 | [11 empty] | 0
2025-03-09 | 7:00 | Breakfast | Judges |  |  | 0 | [11 empty] | 0
2025-03-09 | 10:00 | Snack | Judges |  |  | 0 | [11 empty] | 0
2025-03-09 | 13:30 | Lunch | General |  |  | 0 | [11 empty] | 0
2025-03-09 | 13:30 | Lunch | Judges |  |  | 0 | [11 empty] | 0
2025-03-09 | 15:00 | Snack | Judges |  |  | 0 | [11 empty] | 0
2025-03-09 | 18:00 | Dinner | General |  |  | 0 | [11 empty] | 0
2025-03-10 | 7:00 | Breakfast | General |  |  | 0 | [11 empty] | 0
2025-03-10 | 7:00 | Breakfast | Judges |  |  | 0 | [11 empty] | 0
2025-03-10 | 10:00 | Snack | Judges |  |  | 0 | [11 empty] | 0
2025-03-10 | 13:30 | Lunch | General |  |  | 0 | [11 empty] | 0
2025-03-10 | 13:30 | Lunch | Judges |  |  | 0 | [11 empty] | 0
2025-03-10 | 15:00 | Snack | Judges |  |  | 0 | [11 empty] | 0
2025-03-10 | 20:00 | Dinner | General |  |  | 0 | [8 empty] | 1 |  |  | -1
Day | Time | Meal | Who? | Meal Count
2024-03-14 | 19:30 | Dinner | General | 10
2024-03-15 | 8:00 | Breakfast | General | 10
2024-03-15 | 12:30 | Lunch | General | 15
2024-03-15 | 18:00 | Dinner | General | 35
2024-03-15 | 18:00 | Dinner | Judges | 25
2024-03-16 | 7:00 | Breakfast | General | 80
2024-03-16 | 7:00 | Breakfast | Judges | 25
2024-03-16 | 10:00 | Snack | Judges | 25
2024-03-16 | 13:30 | Lunch | General | 80
2024-03-16 | 13:30 | Lunch | Judges | 25
2024-03-16 | 15:00 | Snack | Judges | 25
2024-03-16 | 18:00 | Dinner | General | 80
2024-03-17 | 7:00 | Breakfast | General | 80
2024-03-17 | 7:00 | Breakfast | Judges | 25
2024-03-17 | 10:00 | Snack | Judges | 25
2024-03-17 | 13:30 | Lunch | General | 80
2024-03-17 | 13:30 | Lunch | Judges | 25
2024-03-17 | 15:00 | Snack | Judges | 25
2024-03-17 | 20:00 | Dinner | General | 35

## Set up Areas-Specs
VENUE NAME
Event SET-UP AREAS and SPECS
ALL SET UP TO TAKE PLACE ON DAY -1
Please confirm with Event Manager for revisions/updated logistics inofrmation on day of set-up.
Does Venue have a supplier for tables and chairs?
[6 empty] | Venue |  | FIRST
[5 empty] | TOTALS | 0 | 0 | 0 | 0
Areas |  | # | Item | Comments | Venue/FIRST | Required Chairs | Required Tables | Required Chairs | Required Tables
Welcome/Registration Areas (Volunteers and Teams)
Location:
To Be Set By:
|  | 4 | 6' banquet Table
|  | 4 | Chairs
|  | 2 | Table Skirts + Clips
|  | 2 | Tear drop Banner
|  | 2 | Room Signage (Roadcase - ? )
|  | 2 | Easel
Judge's Deliberation Room
Location:
To Be Set By:
|  | 6 | 6' banquet Table (U Shape for 34)
|  | 1 | 6' table for speaker
|  | 1 | 6' banquets draped for material display
|  | 2 | 6' banquets draped for foodservice
|  | 3 | Table Skirts (buffet)
|  | 1 | Projector
|  | 1 | Screen
|  | 20 | Chairs
|  | 2 | Keys to the Room
Event Office
Location:
To Be Set By:
|  | 2 | 6' banquet Table
|  | 1 | 6' banquets Table (radios)
|  | 4 | Chairs
|  | 2 | Keys
|  | 2 | Electrical power access
|  | 1 | High Speed Internet Connection
The FIRST Impact Room (previously Chairmans Rooms)
Location:
To Be Set By:
|  | 1 | 6' banquet Table
|  | 1 | Table Skirt
|  | 3 | Chairs
|  | 1 | Easel Outside room
Dean's List Interview Room
Location:
To Be Set By:
|  | 1 | 6' banquet Table
|  | 1 | Table Skirt
|  | 3 | Chairs
|  | 1 | Easel Outside room
Pit Admin Area + Spare Parts
Location:
To Be Set By:
|  | 4 | 6' banquet
|  | 4 | Table Skirts
|  | 2 | Easel
|  | 6 | Chairs
|  | 1 | Internet Connection
|  | 1 | 10amp drop Power
Practice Field Area (Carpet is 15x30")
Location:
To Be Set By:
|  | 1 | 6' banquet Table
|  | 1 | Table Skirts
|  | 2 | Chairs
|  | 1 | Easel
|  | 50'-60' | 3' pipe and drape
Safety Stations (based on 2 stations)
Location:
To Be Set By:
|  | 1 | 6' banquet Table
|  | 0 | Table Skirts
|  | 3 | Easel (for safety messaging)
|  | 0 | Chairs
Inspection Area
Location:
To Be Set By:
|  | 2 | 6' banquet Table
|  | 2 | Table Skirts
|  | 1 | Easel
|  | 1 | Large Dry Erase Board
|  | 4 | Chairs
|  | 1 | Electrical Wall Outlet (refer to pit drawing)
Pit Booths (based on 26-38 PIT's)
Location:
To Be Set By:
|  | 31 | Team Booth Sets Each to Include:
|  | 1 | 8' Upright Pole with "S" hook (not mandatory)
|  | 1 | 6' Banquet Table
|  | 1 | Team ID Sign
|  | 1 | 10' amp drop per pit booth
Playing Field (FMS Table)
Location:
To Be Set By:
|  | 4 | 6' banquets Table -scoring
|  | 4 | Table Skirts
|  | 30' | 3' Pipe and Drape Scoring
|  | 300' | 3' Pipe and Drape around playing field
|  | 18 | Chairs (6 FMS and 12 Field reset)
|  | 1 | 20 amp drop - FMS (must be separate circuit)
|  | 1 | 30 amp drop - Field Lighting (must be separate circuit)
|  | 1 | High Speed Internet Line
Judges' / Seating Area - Field Side End Of Day
Location:
To Be Set By:
|  | 20 | Chairs - padded from Athletics
Production Area (AV & DJ)
Location:
To Be Set By:
|  | 4 | 6' banquet Table
|  | 1 | Elevated Chair (Camera person)
|  | 4 | Chairs
Webcast
Location:
| Description |  | 6x6' space, near electrical source
To Be Set By:
|  | 2 | Chairs
|  | 1 | Electrical outlet
|  | 1 | High Speed Internet Line (from AV)
FIRST Swag Booth
Location:
To Be Set By:
|  | 1 | 6' banquet Table
|  | 1 | Table Skirts
|  | 1 | FIRST Badge Banner
|  | 2 | Chairs
|  | 1 | Electrical Outlet
|  | 1 | Internet Hardline (for surveys)
Machine Shop
Location:
To Be Set By:
6' banquet Table
Table Skirts
Chairs
Venue Booth (optional to Venue)
Location:
To Be Set By:
|  | 2 | 6' banquet draped/skirted
|  | 4 | Chairs
|  | 2 | Easels
|  | 1 | 20 amp outlet (existing)
Volunteer Lounge (to accommodate for 78 volunteers)
Location:
To Be Set By:
|  | 14 | 6' banquet Table (Seating)
|  | 70 | Chairs
|  | 6 | 6' banquet Tables Skirted (Catering)
|  | 1 | Easel
|  | 2 | Folding Coatracks
Mentor Lounge (requirements depending on venue)
Location:
To Be Set By:
|  | 1 | 6' banquet Table (Catering)
|  | 1 | Table Skirts
|  | 20 | Chairs (for mentors to sit)
|  | 2 | Tables for mentors to work)
|  | 1 | Easel Outside room
Quiet Room
Location:
To Be Set By:
|  | 4 | 6' banquet Tables
|  | 4 | Table Skirts
|  | 10 | Chairs
Banners
Location:
To Be Set By:
|  | 1 | Welcome to FIRST (tall/narrow)
|  | 1 | Photo permission (tall/narrow)
|  | 2 | All programs pull up banner
|  | 1 | Mission pull up banner
|  | 1 | FLL Explore pull up banner - logo
|  | 1 | FLL Challenge pull up banner - logo
|  | 1 | FTC pull up banner - logo
|  | 1 | FRC pull up banner - logo
|  | 1 | FRC pull up banner - photos
|  | 1 | All programs - 10x8
|  | 1 | FIRST logo repeat - 10x8
|  | 2 | Game banner
Prayer Space
Location:
To Be Set By:
|  | 4 | Chairs
|  | 1 | Table
|  | 1 | Adequate space on the floor
CanCode Booth
Location:
To Be Set By:
This maybe a 10x10 space near PIT Admin (see map)
Tables/chairs/displays/laptops etc. will arrive on FIRST Truck
Laptops will be in the Volunteer Road case that needs to be handed
Power outlet for the booth (power 6 laptops)
Internet Hardline (could be taken from SWAG or PIT)
FTC, FLL Challenge, FLL Explore, FLL Discover Displays (based on what the event will have)
Location:
To Be Set By:
|  | 4 | 6' banquet Table
|  | 4 | Table Skirts
|  | 8 | Chairs
|  | 1 | FLL Explore pull up banner - photos
|  | 1 | FLL Challenge pull up banner - photos
|  | 1 | FTC pull up banner - photos

## Guest Speakers
VENUE NAME
GUEST SPEAKERS
Recommend no more than 2 speakers per Agenda Activity
Day | Date | Time | Agenda Activity | Speaker # | Speaker Name | Title | Company | Contact # | Email | Confirmed Y/N | On-Site Contact
1 | Day 1 |  | Opening Ceremonies | 1
1 | Day 1 |  | Opening Ceremonies | 2
1 | Day 1 |  | Opening Ceremonies | 3
2 | Day 2 |  | Opening Ceremonies | 1
2 | Day 2 |  | Opening Ceremonies | 2
2 | Day 2 |  | Opening Ceremonies | 2

## 2020 Volunteers (hidden)
FIRST assigns this person - Volunteer Coordinator |  |  |  |  | VOLUNTEERS |  |  | Volunteer Management System Link
Forumla driven cell, please do not change | ADD Colour Coding for Requirements
Role | Age | FIRST Exper | Target % Gender (if F:1) | Total # Volunteers | Volunteer Name | Mark VMS Assigment Confirmed (Yes) | Thur PM (input "1") | Fri AM (input "1") | Fri PM (input "1") | Sat (input "1") | Sun (input "1") | Email Address | Cell Phone # | Company
KEY VOLUNTEER ROLES | Age
*Volunteer Coordinator (FIRST Assigns) | 23 | x |  | 1 | #REF! | Yes | 1 | 1 | 1 | 1 | 1
Volunteer Coordinator (in Training) (FIRST Assigns) | 23 |  |  |  | #REF! | N/A
*FTA #1 - FIRST Assigns | 19 | x |  | 1 | #REF! | Yes | 1 | 1 | 1 | 1 | 1
*FTA #2 - FIRST Assigns |  |  |  | 1 | #REF! | Yes | 1 | 1 | 1 | 1 | 1
*FTAA (Assistant ) | 19 | x |  |  | #REF!
*Field Supervisor - FIRST Assigns | 19 | x |  | 1 | #REF! | Yes | 1 | 1 | 1 | 1 | 1
*Field Supervisor Trainee - (EDI) - FIRST Assigns | 19 | x |  |  | #REF! | N/A
*Head Referee - FIRST Canada Assigns | 23 | x |  | 1 | #REF! | Yes |  | 1 | 1 | 1 | 1
*Referee 1 - FIRST Assigns | 19 | x | 1 | 1 | #REF! | Yes |  |  | 1 | 1 | 1
*Referee 2 - FIRST Assigns | 19 | x |  | 1 | #REF! | Yes |  |  | 1 | 1 | 1
*Referee 3 - FIRST Assigns | 19 | x | 1 | 1 | #REF! | Yes |  |  | 1 | 1 | 1
*Referee 4 - FIRST Assigns | 19 | x |  | 1 | #REF! | Yes |  |  | 1 | 1 | 1
*Referee 5 - FIRST Assigns | 19 | x |  | 1 | #REF! | Yes |  |  | 1 | 1 | 1
*Referee 6 - FIRST Assigns | 19 | x |  | 1 | #REF!
*Lead Robot Inspector - FIRST Assigns | 21 | x |  | 1 | #REF! | Yes |  |  | 1 | 1 | 1
*Control System Advisor - FIRST Assigns | 19 | x |  | 1 | #REF!
*CSA Trainee (EDI) - FIRST Assigns | 19 |  | 1 | 1 | #REF! | Yes |  |  | 1 | 1 | 1
*Judge Advisor - FIRST Canada Assigns | 26 | x |  | 1 | #REF! | Yes |  |  | 1 | 1 | 1
*MC - Primary FIRST Assigns | 19 | x |  | 1 | #REF! | Yes |  |  | 1 | 1 | 1
*MC - Secondary (Optional) FIRST Assigns | 19 |  |  |  | #REF!
*GA - Primary FIRST Assigns | 19 | x | 1 | 1 | #REF! | Yes |  |  | 1 | 1 | 1
*GA - Secondary (Optional) - FIRST Assigns | 19 |  |  | 1 | #REF! | Yes | 1 | 1 | 1 | 1 | 1
UL Safety Advisor (assigned by UL) or Safety Manager 1 |  |  | 1 | 1 | #REF! | Yes |  |  | 1 | 1 | 1
Safety Manager 2 |  |  |  | 1 | Brandon Tran | Yes |  |  | 1 | 1 | 1
Lead Team Queuer | 19 | x |  | 1 | Alex Churcher | Yes |  | 1 | 1 | 1 | 1
Scorekeeper | 19 | x |  | 1 | Zachary Seguin | Yes |  | 1 | 1 | 1 | 1
Scorekeeper Trainee (if applicable) |  |  |  |  | N/A
Judge Advisor Assistant (See FIRST Criteria) | 19 |  | 1 | 1 | Elizabeth Del Genio | Yes |  |  | 1 | 1 | 1
Pit Administration Supervisor | 19 | x | 1 | 1 | Kathy Wilcox | Yes |  | 1 | 1 | 1 | 1
Pit Admin Trainee - EDI focus/lens | 19 |  |  | 1 | Sayfullah Eid |  | 1 |  | 1 | 1 | 1
Pit Administration Support and Spare Parts | 19 | x | 1 | 1 | Bev Carmichael/ Mackenzie Willis | Yes |  | 2 | 2 | 2 | 2
Pit Announcer | 18 | 1 | 1 | 1 | Megan McEwen | Yes |  |  | 1 | 1 | 1
Robot Inspector (Day0 PM/1/2) 1 - NEW | 18 |  | 1 | 1 | Aylene Gracie | Yes |  |  | 1
Robot Inspector (Day0 PM/1/2) 2 | 18 |  |  | 1 | Roland Sing | Yes |  |  | 1 | 1 | 1
Robot Inspector (Day0 PM/1/2) 3 | 18 |  |  | 1 | Aaron vandenEnden | Yes |  |  | 1 | 1 | 1
Robot Inspector 4 - *EDI; female, under represented | 18 |  |  | 1 | Keenan Akit | Yes |  |  | 1 | 1 | 1
Robot Inspector 5 - NEW | 18 |  |  | 1 | Jayton McCracken | Yes |  |  | 1 | 1 | 1
Robot Inspector 6 - NEW | 18 |  |  | 1 | Matthew Harris | Yes |  |  | 1 | 1 | 1
Robot Inspector 7 | 18 |  |  | 1 | Victor Haines | Yes |  |  | 1 | 1 | 1
Robot Inspector 8 | 18 |  |  | 1 | Jake Chapeskie | Yes |  |  | 1 | 1 | 1
Robot Inspector 9 | 18 |  |  | 1 | Marcus kubilius | Yes |  |  | 1 | 1 | 1
Robot Inspector 10 | 18 |  |  | 1 | Paul Gooderham-Belanger | Yes |  |  | 1 | 1 | 1
Machine Shop Provided by |  |  |  | 1 | FIRST
Anthem Singer |  | x | 1 | 1 | Deanna Singh
Photographer |  | x | 1 | 1 | Cathy Loomes | Yes |  |  | 1 | 1 | 1
SWAG Booth (T-Shirt Sales) (FIRST assigns) |  | x |  | 1 | #REF!
CanCode Booth (add Yes or No) (FIRST assigns) |  | x |  | 1 | #REF!
Team Queuing 1 (recruit a female) |  |  |  | 1 | Saihajpreet Singh | Yes |  |  | 1 | 1 | 1
Team Queuing 2 (recruit a female) |  |  |  | 1 | Lukas Melanson | Yes |  |  | 1 | 1 | 1
Team Queuing 3 |  |  |  | 1 | Serban Popovici | Yes |  |  |  | 1 | 1
Team Queuing 4 |  |  | 1 | 1 | Oluwafikunmi Kilanko | Yes |  |  | 1 | 1 | 1
Field Repair/Reset |  |  |  | 1 | Mark Zachkewich | Yes |  |  | 1 | 1 | 1
Field Repair/Reset |  |  | 1 | 1 | Emma Douglas | Yes |  |  | 1 | 1 | 1
Field Repair/Reset |  |  |  | 1 | Ryan McTaggart | Yes |  |  | 1 | 1 | 1
Field Repair/Reset |  |  | 1 | 1 | Linette Brown | Yes |  |  |  | 1 | 1
Field Repair/Reset |  |  |  | 1 | Ray Fan | Yes |  |  |  |  | 1
Field Repair/Reset |  |  | 1 | 1 | Camille Adams | Yes |  |  | 1 | 1 | 1
Field Repair/Reset |  |  |  | 1 | David Gunn | Yes |  |  | 1 | 1 | 1
Field Repair/Reset |  |  |  | 1 | Jordan Wallace | Yes |  |  | 1 | 1 | 1
Field Repair/Reset |  |  |  | 1 | Kale Wallingford | Yes |  | 1 | 1 | 1 | 1
Field Repair/Reset |  |  |  | 1 | Anthony Koziol | Yes |  |  |  | 1 | 1
Field Repair/Reset |  |  |  | 1 | Dhriti Aravind | Yes |  |  |  | 1 | 1
Field Repair/Reset |  |  |  | 1 | Kevin McCloy | Yes |  |  | 1 | 1 | 1
Field Repair/Reset |  |  |  | 1
Practice Field Attendant |  |  |  | 1 | Robert Mah | Yes |  |  | 1 | 1 | 1
Practice Field Attendant |  |  | 1 | 1 | Robin Feeney | Yes |  |  | 1 | 1 | 1
Team Load In /Out (Fri 1-6PM, Sun 2-9PM) |  |  |  | 1 | Rena Chen | Yes |  |  | 1 | 1 | 1
Team Load In /Out (Fri 1-6PM, Sun 2-9PM) |  |  |  | 1
Team Load In /Out (Fri 1-6PM, Sun 2-9PM) |  |  |  | 1
Team Load In /Out (Fri 1-6PM, Sun 2-9PM) |  |  |  | 1
Quiet Room Attendant/Safety Glasses Attendant / Practice Field 1 |  |  |  | 1 | Dorothy Caldwell |  |  |  | 1
Quiet Room Attendant/Safety Glasses Attendant / Practice Field 2 |  |  |  | 1 | Carol Chai |  |  |  |  | 1 | 1
Quiet Room Attendant/Safety Glasses Attendant / Practice Field 3 |  |  |  | 1 | Laura Prado |  |  |  | 1 | 1 | 1
Quiet Room Attendant/Safety Glasses Attendant / Practice Field 4
Quiet Room Attendant/Safety Glasses Attendant / Practice Field 5
Field Assebly (required on Field set up/takedown - truss) -1 |  |  |  |  | Alex Churcher |  |  | 1
Field Assebly (required on Field set up/takedown - truss) -2 |  |  |  |  | Brian Caldwell |  |  | 1
Field Assebly (required on Field set up/takedown - truss) -3 |  |  |  |  | Anthony Koziol |  |  | 1
Field Assebly (required on Field set up/takedown - truss) -4 |  |  |  |  | Erik Caldwell |  |  | 1
Field Assebly (required on Field set up/takedown - truss) -5 |  |  |  |  | John Chalrton |  |  | 1
Field Assebly (required on Field set up/takedown - truss) -6 |  |  |  |  | David Gunn |  |  | 1
Field Assebly (required on Field set up/takedown - truss) -7 |  |  |  |  | Sid Toutah |  |  | 1
Field Assebly (required on Field set up/takedown - truss) -8 |  |  |  |  | Micheal Chruchill |  |  | 1
Field Assebly (required on Field set up/takedown - truss) -9 |  |  |  |  | Zachary Seguin |  |  | 1
Field Assebly (required on Field set up/takedown - truss) -10 |  |  |  |  | Marcus Kubilius |  |  | 1
TOTAL FEMALE % VOLUNTEERS/JUDGE |  | 25.84% | 17 | 65 |  |  |  | 12 | 51 | 54 | 55
Judges below (add names from VMS to track Gender balance) |  | 25% | 6 | 24 |  |  |  | 0 | 21 | 22 | 22
Judge Advisor - FIRST Canada Assigns | 26 | x |  | 1 | James Del Genio | Yes |  | 1 | 1 | 1 | 1 |  |  | 5ofus.com
Judge 1 | 23 | x |  | 1 | Graham Eatherley | Yes |  |  | 1 | 1 | 1 |  |  | Carleton University
Judge 2 | 23 | x |  | 1 | James Diak | Yes |  |  | 1 | 1 | 1 |  |  | Carleton University
Judge 3 | 23 | x |  | 1 | Jim Forbes | Yes |  |  |  | 1 | 1
Judge 4 | 23 | x |  | 1 | Lawrence Lupton | Yes |  |  | 1 | 1 | 1
Judge 5 | 23 | x | 1 | 1 | Derek Glennie | Yes |  |  | 1 | 1 | 1 |  |  | Spartan Bioscience
Judge 6 | 23 | x | 1 | 1 | James Cann | Yes |  |  | 1 | 1 | 1 |  |  | Carleton University
Judge 7 | 23 | x |  | 1 | Gabrielle Sevigny | Yes |  |  | 1 | 1 | 1 |  |  | Carleton University
Judge 8 | 23 | x | 1 | 1 | Claire McLaughlin | Yes |  |  | 1 | 1 | 1
Judge 9 | 23 | x | 1 | 1 | Daniel Wang | Yes |  |  | 1 | 1 | 1
Judge 10 | 23 | x |  | 1 | Bruce Burlton | Yes |  |  | 1 | 1 | 1 |  |  | Carleton University | 647-898-4365
Judge 11 | 23 | x |  | 1 | Tom Morrice | Yes |  |  | 1 | 1 | 1 |  |  | Carleton University | 647-717-2989
Judge 12 | 23 | x |  | 1 | Teresa Sing | Yes |  |  | 1 | 1 | 1 |  |  |  | 647-667-9337
Judge 13 | 23 |  | 1 | 1 | Charles Macdonald | Yes |  |  | 1 | 1 | 1 |  |  | Carleton University
Judge 14 | 23 |  |  | 1 | Albin Pothen | Yes |  |  | 1 | 1 | 1 |  |  | Ross Video
Judge 15 | 23 |  |  | 1 | Dan Fortin | Yes |  |  | 1 | 1 | 1
Judge 16 | 23 |  |  | 1 | Rajesh Dawadi | Screening |  |  | 1 | 1 | 1 |  |  | Ericsson
Judge 17 | 23 |  |  | 1 | Pieter Wessel | Yes |  |  | 1 | 1 | 1
Judge 18 | 23 |  |  | 1 | Dimple Thomas | Screening |  |  | 1 | 1 | 1 |  |  | Ericsson
Judge 19 | 23 |  |  | 1 | Kyle Stitt | Yes |  |  | 1 | 1 | 1 |  |  | General Dynamics
Judge 20 | 23 |  | 1 | 1 | Kyle Lunau | Yes |  |  | 1 | 1 | 1 |  |  | General Dynamics
Judge 21 | 23 |  |  | 1 | John Shaw | Yes |  |  | 1 | 1 | 1
Judge 22 | 23 |  |  | 1 | Isaac Tsang | Yes |  |  | 1 | 1 | 1 |  |  | The Ottawa Hospital
Judge 23 | 23 |  |  | 1
Judge 24 | 23 |  |  | 1
FC - Mark Breadner | STAFF | x |  | 1
FC - Kim Cooper | STAFF | x
FC - John Hobbins | STAFF | x |  | 1 |  |  |  | 1 | 1 | 1 | 1
FC - Dave Ellis | STAFF | x
FC - Arti Javeri | STAFF | x
FC - Christine Bibic | STAFF | x |  | 1
FC - Florence Lee | STAFF | x
FC - George Chisolm | STAFF | x
FC - Paul Keenan | STAFF | x |  | 1
FC - Melissa Douglas | STAFF | x
FC - Annika Pint | STAFF | x
FC - Sheri-LynnKoscielski | STAFF | x |  | 1
FC - Heather Kelso | STAFF | x |  | 1 |  |  |  | 1 | 1 | 1 | 1
FC - Dorelle Joynt | STAFF | x
FC - Dawn Brillinger | STAFF | x
AV Team | AV Team | x |  | 3 |  |  |  | 3 | 3 | 3 | 3
|  | TOTAL | 0 | 9 | Staff/AV
|  | TOTAL |  | 89 | Total Volunteers including Judges and STAFF |  |  | 12 | 72 | 76 | 77
|  | TOTAL |  | 74 | Total Volunteers WITHOUT Judges (incl. STAFF) |  |  | 12 | 51 | 54 | 55
Note on A96: ====== ID#AAABPH-_wzk Please note that you take special attention to the the below when recruiting for Judge Advisor Assistant Role. The general roles, responsibilities and criteria are mentioned here, please also note the 2 additional items below that need to be considered when recruiting for this role (2024-06-03 13:22:22) - Judge advisor assistants cannot be a parent of a student participating in the FRC program. - Judge advisor assistants cannot be an FRC mentor (active or not) -Arti Javeri

## Capacity (hidden)
Durham (38)
Western (38)
McMaster (38)
Venue (38)
York (36)
North Bay (36)
Georgian (30)
Waterloo (32)

## Other items (hidden)
To-Do-Items
FORKLIFT REQUIRED
Tables, chairs Vol Lounge
Tables, chairs pit, pit admin, safety glasses, other
Pip and Drape for Mentor Lounge
FIRST Pipe and Drape - available to venues | Height, width, length in feet
17' h x 10'w = 70'
4-5'h x 10'w = 60'
3'h x 10'w = 280'
To-Do-Items
Venue Pipe and Drape needs | FORKLIFT REQUIRED
- game field area
- pit areas
practice field | Tables, chairs Vol Lounge
- Vol Lounge | Tables, chairs pit, pit admin, safety glasses, other
Pip and Drape for Mentor Lounge
Electrical Needs | FIRST Pipe and Drape - available to venues | Height, width, length in feet
wheel chair cable covers |  | 17' h x 10'w = 70'
cable covers |  | 4-5'h x 10'w = 60'
pit power distribution grid - 36 x 110v |  | 3'h x 10'w = 280'
pit admin - 2 x 110v outlets to |  | 8'h x 10'w = 60'
FMS - 2 x 20amp 110v outlets
Venue Pipe and Drape needs
- game field area
- pit areas
practice field
- Vol Lounge
| Electrical Needs |  | 40 pits, 2 x 20amp to FMS, Pit Admin, AV needs, 10 wheel chair cable covers
| wheel chair cable covers | confirmed and quote submitted
cable covers
pit power distribution grid - 36 x 110v
pit admin - 2 x 110v outlets to
FMS - 2 x 20amp 110v outlets

## Humber 2020 Detailed Schedule (hidden)
Venue District Event | [5 empty] | Follow Up Items
| 32 Teams | 7.0 Min. Cycle Times | Qualification Matches = 12 hours
Date | Day | TIME |  | # Vol's required | Food Count | Actions: | Questions for Lynn | Details
*note - Event Set Up TASK work sheet here
https://drive.google.com/open?id=1JdZZ0Hu0yhV97kvXWhzuvg8gKr76u2Gb5F4aU3OZp3A
Day -2 | 2020-03-04 | 21:00 | Tarp laid in gym - Bleacher Set in position | 0 |  |  | Humber Movers | WO #24321
|  | ThursSTART | Loading areas cleared and available for load-in
Day -1 | Day -1 Mar 5 | 7:00 | FIRST and 6 Humber staff - Wood Set in place 7-11am | 8+ |  | Timmy's | arti, john, paul, kim, ?
|  | 9:45 | 8-10 Volunteers and helpers ready to assist with unloading | 10 |  |  | Romaine, Michael, Eric, Danny, Randy, Shaun, Farzad, Carl, | field set up, unload truck, unroll carpet
|  | 11:00 | FC Truck arrives***timing and movement of plywood for whole floor - forklift | 6 |  | Forklift req'd
|  | 23:30 | Pit set layout - FIRST assigned volunteers | 3
|  | 12 noon | Lunch - fieldside |  | 12 | Subway
Pre-shipped packages brought to Event Office
|  |  | Layout PITS (markings and drawings) should we hire outside for this? | 3
|  | 14:45 | Volunteer help to unload carpet with Electric Contractors
|  | 15:00 | Electric Contractors (carpet and electrical work) | 4
|  |  | Pit electricity to be laid, cable mats, wheel chair mats to be installed by contractor | 0
|  | 17:00 | Dinner - fieldside (10 grab and go) |  | 10 | Pizza
|  | 18:00 | AV Contractors Truck unloads only - (8 am set up Day 0)
TBD |  |  | GRAB Production (AV) arrive unload trucks
TBD | FIRST Staff duties | 10:00am - 8:00 pm | • Unload FIRST truck (forklift) and assign road-cases to the appropriate areas. *Pit electricity to be laid, cable mats, wheel chair mats to be installed • Carpet layout done and then rolled, taped, vacuumed • Field perimeter road cases positioned • VIP space set up - Day 0 • Set up SWAG - As per Paul |  |  |  | • who is required • who is required • who is required • who is required • who is required • who is required
TBD
Security | 8:00PM-7:00AM | not needed
Day 0 | Day 0 Mar 6 | Day 0 Tasks | Ensure Replenishment (Consumables) road-case (that arrives with AV:GRAB) materials are sent to the right areas |  | yes - 1 hour
|  | 7:00 | FIRST and Humber representatives arrive
|  | 7:45 | Set Up crew
Lynn, John, EM meet and brief about the day
| Complete tasks that were not done on Day -1 |  | Field Setup and Event set up continues - Main feild setup - PIT setp (PIT Admin, ensure viewing area is clear, pipe and drape is done, Machine shop area is clear, practice area is pipe and draped) - Create walkway for teams in/out of the main field + pipe and drape or extensions to divide group - Signage and directional signage - Judges rooms, Volunteers rooms and Interview rooms - Corridor free of hazards / safety check - Load-in Area defined and clear
EMT | 3:00PM-8:00PM | 8:00 | Set up crew volunteers (FTA/CSA/PITAdmin...)AV Contractors, FTA and FS crew arrives
|  | 8:00 | Breakfast snack fieldside (25 count) |  | 25
- Confirm plans to shut down WIFI Date/Day at 12:00PM Day 0 until Day 2 8PM
|  | 11:00 | Meet with Parking Attendant to go over the Load-in and Load-out
PITS should be complete (other than practice field)
|  | 12:00 | Lunch (35 people) Verify phone lines; Network drop on floor with house |  | 35
|  | 13:00 | PIT completion and Practice Field set up
Set rooms as per - set up specs document
|  | 14:45 | Team Load-in Coordinator - LRI, prepare to recieve teams
|  | 3:00-5:00PM | Team LOAD-IN (one hour team pit set up) Team LOAD-IN & PITS OPEN - *Teams welcomed, staff visiting vehicles to greet teams, onsite activities, flyers, map to E135 |  | Romaine Waite, Lynn to send john info about E135 | Romaine Waite
|  | 16:30 | Inspector Dinner - rotating so as to monitor Load-in of teams
|  | 17:00 | Dinner - rotating with key roles at work positions |  |  |  |  | 40 vehicles - truck/trailers
|  | 17:00 | PITS OPEN to all, robot inspections
|  | 17:00 | Judges meet, ensure JA and Safety Advisors connect
|  | 5:30 PM - 8:00 PM | Rooms set up - Volunteer Lounge, Committee room, Mentor Lounge set up • Judges room – meeting rooms (*available after 6pm) eat in B101, then go to C110 judges room • Chairman’s Award interview – room # • Dean’s List – room #
|  | 17:30 | Team filler line matches until 7:30pm, robot calibration
|  | 18:00 | Judges arrive - intitial meeting room for judges B101, meet 6-9pm, Lynn or EM to ensure SA is connected with the JA
|  | 18:30 | Judges Dinner - room timing TBC
|  | 19:30 | Matches completed, field preparation, end time dependent on FTA |  |  |  |  | *no team Load-in after 8pm
|  | 19:45 | Review the overnight requirements, EM informs Key Vol of 7:30am SHARP next day meeting in event office
|  | 20:00 | PITS CLOSE
2020-03-07 | Day 1, March 7 | 6:45 | FIRST STAFF ARRIVE, Event Managers |  |  |  |  | 80% will attend
EMT (8:00AM-8:00PM) |  | 7:00 | BREAKFAST FOR VOLUNTEERS |  | 95
|  | 7:30 | Key role meeting
|  | 8:00 | PITS OPEN
|  | 9:00 | Drivers Meeting on main field
|  | 9:30 | Practice Matches (9:30-10:45am)
|  | 11:00 | OPENING CEREMONIES
|  | plaque | Geraldine Babcock - Director, Community Outreach and Workforce Development
Chris Whitaker, CEO Humber College
|  | 11:30 | MATCHES BEGIN
|  | 13:30 | LUNCH BEGINS |  | 100
|  | 2:30pm | MATCH PLAY RESUMES (2:30-7:00pm)
|  | 17:30 | Dinner (ensure easy access for field crews working - have 8-10 boxed dinner containers available, in case of running late)
|  | 19:45 | EM advises key role volunteers about NO 7:30am SHARP morning meeting, but KRL's to report in to FC lead
Security (7:45PM-7:00AM) |  | 19:45 | Security arrives - N/A
|  | 20:00 | PITS CLOSE
2020-03-08 | Day 2, March 8 | 6:45 | FIRST STAFF ARRIVE, SHOW READY
EMT (8:00AM-6:00PM) |  | 7:00 | BREAKFAST FOR VOLUNTEERS |  | 100
|  | 7:30 | NO Key role meeting - KRL's report to FC lead for check in
|  | 8:00 | PITS OPEN
|  | 9:00 | OPENING CEREMONIES
| 2020-03-08 | 9:00 | Opening Ceremonies
Enbridge - Mark Grimley, Manager of Operaations, Kelfeld & Station B Toronto Region Operations
guest speakers?
|  | 09:30:00 | MATCHES BEGIN (9:30-11:30am)
|  | 10:30 | judges (refresh beverages and light food) |  |  | Chartwell's - donated
|  | 11:00 | EM to bring Rookie Plaaques to FMS table for presenting at 11:30am
|  | 11:30 | ALLIANCE SELECTIONS
|  | 12:00 | LUNCH BEGINS |  | 100
|  | 13:00 | ELIMINATION ROUNDS BEGIN (3 HOURS)
|  | 15:30 | judges (refresh beverages and light food) |  |  | Chartwell's - donated
|  | 16:00 | AWARDS (4-5:30pm)
|  | 6:00pm | PITS CLOSE
Tear Down Process
|  | 17:30 | Electric Contractors arrives to start tear down, truck loads up
|  | 18:00 | AV Truck tear down begins, loads up
Fork Lift - 8pm-11pm |  | 19:30 | Electric Contractors truck loads up
|  | 20:30 | AV Truck loads up
|  | 21:30 | FIRST Transport loads up
|  | 22:30 | Building cleared
|  | 19:30 | AV begins tear down, 9:00pm Truck loads up
|  | 21:00 | Electrical Truck loads up
|  | 21:30 | AV truck loads up
|  | 22:00 | FIRST Transport loads up
|  | 23:00 | Building cleared

## Waterloo 2020 Detailed Schedule (hidden)
| 29 Teams | 9.0 Min. Cycle Times | Qualification Matches = 12 hours
Requires response by John H.
if john changes something
Katlin Changed Something
Date | Day -1 | TIME | Comments | #Vol's Req'd | Food Count | Details
|  | 15:00 | John to arrive for planning with Katlin/Miki/Peter
|  | 16:00 | Katlin arrives | 2020-08-06 |  | jamie,
| LE tie in early | 4:00:00 | Electric Contractorsian to coordinate with Waterloo electrician | 4
2020-03-18 | WEDNESDAY Day -1
|  | 15:00 | need parking passses for 10 vehicles
2-6pm | PARKING | 14:00 | Block off all spots to make room for transport arriving at 4:30pm
|  | 16:00 | Hahn arrives to layout pits
4:30-7:30pm | Forklift scheduled | 16:30 | FIRST Truck unloads +4 Waterloo volunteers/helpers | 2020-08-06 |  | FIRST 53' transport
block parking lot PA C, peter to send last years request
|  | 18:30 | *need pit layout set up for electrical placement completed by Hahn | 0 |  | Hahn to arrive and set up pits
|  | 19:00 | Electric Contractors Arrives with carpet *unroll carpet asap | 4 assist with carpet |  | Electric Contractors 26' truck
|  | 19:00 | dinner snack on table in fieldside (sandwiches) |  | 12
|  | 20:00 | AV Contractors truck arrives to unload - no set up |  |  | GRAB 26' truck
Room Setup's - who?, pit set up marking pits for electrical, practice field, pit admin
|  | 20:00 | hand out parking passes for key staff for next day - 15 required
|  | 21:00 | clear building
Security (8:30PM-7:00AM) |  |  | *security needed
2020-03-19 | Day -1 DAY Day 0 | 7:00 | FIRST and Waterloo representatives arrive
|  | 7:30 | Set Up crew
|  | 8:00 | AV Contractors, FTA and FS crew arrives | FTA/FS + 8 |  | 7:00am - 8 Waterloo oganised vol's specifically for set up work
|  | 8:00 | light Breakfast snack fieldside |  | 25
|  | 12:00 | Lunch field side to promote continuous working |  | 35
1-6pm | PARKING |  | Prepare lot for 30 vehicles unloading between 2:45-6pm
|  | 2:45:00pm | LRI begins Coordinating Team Load-in
EMT (3:00-8PM) |  | 3:00 - 5:00 PM | Team LOAD-IN & PITS OPEN - *Teams welcomed, staff visiting vehicles to greet teams, onsite activities, flyers | 4 assist with Load-in
|  | 16:45 | Inspector Dinner - rotating so as to monitor Load-in of teams
|  | 5pm | Volunteer Dinner - vol lounge |  | 70
|  | 17:00 | Pits Open and Inspection
|  | 17:30 | Team filler line matches until 7:30pm, robot calibration
JA & Safety Advisors to be introduced by FC Lead and/or EM
|  | 18:00 | Judges arrive - meeting 6-9pm
|  | 18:30 | judges dinner served |  | 24
|  | 19:30 | Matches completed, field preparation, end time dependent on FTA
|  |  | Match schedule run by FTA and FCL - only if all teams are present |  |  | if not all present, schedule is run in the morning
Security (7:45PM-7:00AM) |  | 19:45 | overnight requirement, EM informs Key Vol of 7:30am SHARP next day meeting in event office
|  | 20:00 | PITS CLOSE
2020-03-20 | Day 0 Day 1 | 6:45 | FIRST STAFF ARRIVE, Event Managers
EMT (8:00AM-8:00PM) |  | 7:00 | BREAKFAST FOR VOLUNTEERS |  | 94 | 70 vol's + 24 judges
|  | 7:30 | Key role meeting
|  | 8:00 | PITS OPEN
|  | 9:00am | Drivers Meeting on main field
|  | 9:30am | Practice Matches (9:30-10:45am)
|  | 11:00 | OPENING CEREMONIES
|  | 11:30 | MATCHES BEGIN
|  | 13:30 | LUNCH BEGINS |  | 94 | 70 vol's + 24 judges
|  | 2:30pm | MATCH PLAY RESUMES (2:30-7:00pm)
|  | 17:30 | Dinner (ensure easy access for field crews working - have 8-10 boxed dinner containers available, in case of running late) |  | 94 | 70 vol's + 24 judges
|  | 19:45 | EM advises key role volunteers about NO 7:30am SHARP morning meeting, but KRL's to report in to FC lead | see rollout
Security (7:45PM-7:00AM) |  | 19:45 | Security arrives
|  | 20:00 | PITS CLOSE
2020-03-21 | Day 1 Day 2 | 6:45 | FIRST STAFF ARRIVE, SHOW READY
EMT (8:00AM-6:00PM) |  | 7:00 | BREAKFAST FOR VOLUNTEERS |  | 94
|  | 7:30 | NO Key role meeting - KRL's report to FC lead for check in
|  | 8:00 | PITS OPEN
|  | 9:00 | OPENING CEREMONIES
|  | 09:30:00 | MATCHES BEGIN (9:30-11:30am)
|  | 10:30 | judges (refresh beverages and light food) |  | 20
|  | 11:30 | ALLIANCE SELECTIONS
|  | 12:00 | LUNCH BEGINS |  | 94 | 70+24 judges
12-7pm | PARKING |  | need to block off all spots alongside PAC for team Load-out
|  | 13:00 | ELIMINATION ROUNDS BEGIN (3 HOURS)
|  | 15:30 | judges (refresh beverages and light food) |  | 20
|  | 16:00 | AWARDS (4-5:30pm)
|  | 18:00 | PITS CLOSE
|  | 17:30 | Electric Contractors arrives to start tear down, truck loads up
|  | 19:30 | Fieldside dinner snacks |  | 25
|  | 18:00 | AV Truck tear down begins, loads up
8pm-11pm | Forklift scheduled | 19:30 | Electric Contractors truck loads up
|  | 20:30 | AV Truck loads up
|  | 21:30 | FIRST Transport loads up
|  | 22:30 | Building cleared

## Windsor 2020 Detailed Schedule (hidden)
Venue District Event (active document changing overtime) | [5 empty] | Follow Up Items
| 30 Teams | 8.5 Min. Cycle Times | Qualification Matches = 12 hours
Date | Day | TIME | Comments | # Vol's required | Dock | Actions: | Questions for Lynn | Details
Note - confirm FIRST access time = flooring previously laid to accommodate
Do we get access in the a.m. or p.m., what time after flooring is done?
*noon goal to have floor covered..Raven's Nest,
confirm time of access on March 7th
Day -1 | Day -1 Mar 12 | 7:45 | FIRST staff | 2+ |  | arti, john, paul, kim, ? |  | field set up, unload truck, unroll carpet
|  | 8:00 | AV crew (they bring 4 people) | 0 | no forklift required | Need Venue Drawings (John), No forklift needed
***timing and movement of plywood for whole floor - forklift
|  | 8:30 | Pit set layout - FIRST assigned volunteers | 0 |  | Hahn will layout pits & chalk them etc. (John to PIT Map/drawing) Arti to provide Spec Sheet (Rooms set up etc,)
|  | 9:00 | Electric Contractors (carpet and electrical work)
|  | 10:00 | FIRST Truck unloads | 6 | yes Forklift |  |  | No union required
|  | 12 noon | Lunch
|  | 1:00 pm | Meet with Parking Attendant to go over the Load-in and Load-out
|  | 2:00 - 5:00 pm | • Pit electricity to be laid, cable mats, wheel chair mats to be installed • Carpet rolled, taped, vacuumed • Field perimeter positioned, connected (Only if PT wants to set up these rooms on Thurs or Fri?) • Volunteer Lounge, Committee room, Mentor Lounge set up • Judges room – meeting rooms • Chairman’s Award interview – room # • Dean’s List – room # • VIP space set up • Set up SWAG • Magna Roll Up Banners |  |  | • who is required • who is required • who is required • who is required • who is required • who is required
| May change if FTA crew can be brought in on day -1 evening. If not, then FIRST Crew and Humber crew go home at 5 or 6pm | 4:00 pm | Pits to be completed (pit admin, signs, inspection, magna roll out banner) |  |  |  | ACCESS to the Buidling (until 10pm)? FIRST will provide details in 24 hrs
|  | 6:00 pm | Deans List, Chairmans Interview Room, FIRST Staff/Safety Advisor Room set up to be completed |  |  |  | Do we have access to rooms on Wed
|  | 5:30 pm | FTA/FS arrive field set up |  |  | when is FTA arrival
|  | 18:30 | dinner staff, AV, others? union?
|  | 10:00 pm | clear building |  |  |  | Check with Emily if we have the building till 10pm
Security | 9:30PM-7:00AM |  | Night Security???
Day 0 | Day 0 Mar 13 | 7:00 am | FIRST key people |  | yes - 1 hour
EMT | 2:00PM-9:00PM | 8:00 | Set up crew volunteers (FTA/CSA/PITAdmin...) breakfast
|  | 10:00 am | Scripts to be reviewed with EM/EMA
|  | 11:00 | Meet with Parking Attendant to go over the Load-in and Load-out
|  | 11:45 | Lunch
|  | 1:00 pm | PITs and Practice Field set up
|  | 2:00-5:00PM | Team LOAD-IN (one hour team pit set up) * elevator available 2-10PM |  |  |  | Change the request to Emily to move itming to 8PM instead of 7 PM | 40 vehicles - truck/trailers
|  | 17:00 | Dinner - rotating with key roles at work positions
|  | 17:00 | PITS OPEN
|  | 6:00 PM - 8:00 PM | PRACTICE MATCHES?
|  | 9:00PM | PITS CLOSE |  |  |  |  | *no team Load-in after 8pm
Security | 8:45PM-6:45AM |  | Night Security
Day 1 | Day 1 Mar 14 | 6:30 | FIRST STAFF ARRIVE, SHOW READY
EMT | 7:30AM-7:30PM | 6:45 | BREAKFAST FOR VOLUNTEERS |  |  |  |  | 80% will attend
|  | 7:30 | PITS OPEN |  | FINAL TEAMS Load-in
|  | 8:00 | Practice Matches
|  | 10:00 | OPENING CEREMONIES
Confirmed Guest Speaker - Venue (Provost: Michael Benarroch)
Confirmed Guest Speaker - Venue (Imogen Coe)
Afghan Team 7329 will be on the floor - Imogen will introduce special guests and they do a wave
Confirmed Guest Speaker - Scotiabank (Arti to confirm name)
|  | 10:30 | MATCHES BEGIN |  |  |  |  | 2.5 hours of match play
|  | 13:00 | LUNCH BEGINS
|  | 14:00 | Confirmed Guest Speaker - Magna (Arti to confirm name)
|  | 14:00 | MATCH PLAY RESUMES |  |  |  |  | 4.5 hours of match play
|  | 4:15 | Dinner begins for Inspectors (rotating dinner)
|  | 5:00 | Dinner for volunteers (rotating dinner)
|  | 18:30 | Match play ends |  |  |  |  | would like to end by 5:30 if possible
Security | 7:15PM-6:45AM | 19:30 | PITS CLOSE |  |  |  |  | caterers can be flexible for early or late
Day 2 | Day 2 Mar 15 | 6:30 | FIRST STAFF ARRIVE, SHOW READY
EMT | 7:30AM-7:00PM | 6:45 | BREAKFAST FOR VOLUNTEERS
|  | 7:30 | PITS OPEN
|  | 8:30 | OPENING CEREMONIES
Confirmed Guest Speaker - Venue (Victoria/Arti to confirm name)
|  | 9:00 | MATCHES BEGIN |  |  |  |  | 3.5 hours of match play = 10.5 total qualification rounds
|  | 12:15 | Confirmed Guest Presentation - (12:15) Cheque by RBC PH&N Investment Counsel
|  | 12:30 | ALLIANCE SELECTIONS
|  | 13:00 | LUNCH BEGINS
|  | 14:00 | ELIMINATION ROUNDS BEGIN |  |  |  |  | 3.0 hours of Elemination rounds - quarter/semi/finals
|  | 17:00 | AWARDS
Confirmed Guest Speaker - Venue (Victoria/Arti to confirm name)
|  | 19:00 | PITS CLOSE
|  | 8:00 pm | AV Truck loads up
|  | 21:30 | FIRST Transport loads up
|  | 22:30 | Building cleared

## North Bay 2019 Detailed Scehdul (hidden)
| 28 Teams | 9.0 Min. Cycle Times | Qualification Matches = 12 hours
Requires response by John H.
Requires response by Georgian
Date | Day -1 | TIME | Comments | #Vol's Req'd | Dock | Details
|  | 15:00 | John to arrive to Georgian for planning with Mark
*early access allows electrical early set up
2018-03-14 | Day -1 | 6-10pm | FIRST to hire labour? 4 Georgian people
|  | 18:00 | Set up crew - FIRST (5) | FTA/FS + 8 |  | 4+ volunteers from Georgian?
|  | 18:00 | FIRST Truck unloads +2 Georgian staff, 2 hired labour | 6 for FIRST truck | forklift 6-9pm | FIRST 53', GRAB 26' truck, plus Electric Contractors
|  | 19:00 | AV Contractors truck arrives to unload - no set up
|  | 19:30 | dinner snack on table in field area
Room Setup's - who?, pit set up marking pits for electrical, practice field, pit admin
| LE tie in early | 20:30 | Electric Contractors Arrives with carpet *unroll carpet asap
|  | 22:00 | clear building | 4 assist with carpet |  | Georgian Electrician only available until 4PM. John/Kirsten to coordinate
Security (8:45PM-7:00AM) |  |  | *security needed - yes
| 5-6 volunteers from Mark | January update | *need pit layout set up for electrical placement
2018-03-15 | Day 0 Day 0 | 7:00 | FIRST and Georgain representatives arrive | FTA/FS + 8 +FSM Crew |  | 7:00am - 8 Georgian oganised vol's specifically for set up work
|  | 7:30 | Set Up crew
|  | 8:00 | AV Contractors, FTA and FS crew arrives | 0 | no forklift req'd | truck has lift gate
|  | 8:00 | light Breakfast snack fieldside
|  | 12:00 | Lunch field side to promote continuous working
EMT (3:00-9PM) |  | 3:00 - 4:30 PM | Team LOAD-IN & PITS OPEN | 4 assist with Load-in |  | 30 vehicles - only 5 team members for 1 hour allowed
|  | 16:00 | Inspector Dinner - rotating so as to monitor Load-in of teams |  | inspectors eat 4-5pm | In shifts – on the go
|  | 17:00 | Volunteer Dinner
|  | 16:30 | Pits Open and Inspection
|  | 18:00 | Judges arrive (Tom Lee JA) meeting 6-9pm
|  | 18:30 | judges dinner served
|  | 18:30 | announcement reminder to teams of challenge
|  | 5:30-8 PM | Filler LIne MATCHES / Robot Calibration
Security (8:45PM-7:00AM) |  | 20:45 | overnight requirement
|  | 20:45 | EM informs Key Vol of 7:30am SHARP next day meeting in event office
|  | 21:00 | PITS CLOSE |  |  | *no team Load-in after 8pm
2018-03-16 | Day 1 Day 1 | 6:45 | FIRST STAFF ARRIVE, Event Managers
EMT (8:00AM-8:00PM) |  | 7:00 | BREAKFAST FOR VOLUNTEERS |  |  | 80% will attend
|  | 7:30 | Key role meeting
|  | 8:00 | PITS OPEN |  | FINAL TEAMS Load-in
| 8:30-10 Mentor Breakfast | 8:30 | Drivers Meeting on main field
|  | 9:15 | Practice Matches (9:15-10:45am)
|  | ? | inform teams of fun challenge
|  | 10:30 | judges (refresh beverages and light food)
|  | 11:00 | OPENING CEREMONIES
|  | 11:30 | MATCHES BEGIN
|  | 13:30 | LUNCH BEGINS
|  | 14:30 | MATCH PLAY RESUMES (2:30-7:00pm)
|  | 17:30 | Dinner (ensure easy access for field crews working)
|  | 19:45 | EM advises key role volunteers about 7:30am SHARP morning meeting
Security (7:45PM-7:00AM) |  | 19:45 | Security arrives
|  | 20:00 | PITS CLOSE
2019-03-17 | Day 2 Day 2 | 6:45 | FIRST STAFF ARRIVE, SHOW READY
EMT (8:00AM-7:30PM) |  | 7:00 | BREAKFAST FOR VOLUNTEERS
|  | 7:30 | Key role meeting
|  | 8:00 | PITS OPEN
|  | 9:00 | OPENING CEREMONIES
|  | *09:30:00 | MATCHES BEGIN (9:30-12:45am)
|  | 10:30 | judges (refresh beverages and light food)
|  | 12:00 | winners announcement
|  | 1:00 | ALLIANCE SELECTIONS
|  | 13:30 | LUNCH BEGINS
|  | 14:30 | ELIMINATION ROUNDS BEGIN (3 HOURS)
|  | 15:30 | judges (refresh beverages and light food)
|  | 17:30 | AWARDS (5:30-7:00pm)
|  | 19:30 | PITS CLOSE
|  | 19:00 | Electric Contractors arrives to start tear down, truck loads up |  |  | Georgian Electrician can disconnect on Monday - John/Kirsten to coordinate
|  | 19:30 | AV Truck tear down begins, loads up
Fork Lift - 8pm |  | 20:30 | Electric Contractors truck loads up |  | Fork Lift - 8pm
|  | 21:00 | AV Truck loads up
|  | 21:30 | FIRST Transport loads up
|  | 22:30 | Building cleared
3.0 hours of Elemination rounds - quarter/semi/finals

## Durham 2020 Detailed Schedule (hidden)
Ontario District - Durham College Event - February 27-March 1, 2020
| 36 Teams | 8.5 Min. Cycle Times | Qualification Matches = 12 hours |  | 58 vol/21 judge
Date | Day | Time | Comments | # Volunteers | Food Count | Dock | Details | Actions
Day -1, February 27, 2020 | Day -1 DAY -1 | 10:00 | Set up crew - FIRST reps | 2+
|  | 10:15 | Pit layouts required to be done (chalk lines) | 4+
SET UP PITS BEFORE Electric Contractors ARRIVES |  |  | This means taping the floor for pit locations, identifying practice field location. and having pit drawing available for Litte Electric | Kyle and Dave to handle this
|  | 12:00 | Lunch field side table for FC staff (just order something based on who is there) Burrito Bowls | Dave, Dorelle, Kyle | 3
|  | 13:00 | FIRST 53' transport for unloading | NEED 6-8 PEOPLE Dave, Dorelle, Kyle, Person4, Person5, Person6, Person7, Person8 | 8 | Forklift booked 12-3 | 53' transport truck
|  | 14:00 | Electric Contractors Truck & carpet arrival, complete as much non-field set up done as possible | 4 to help unload carpet |  | Forklift booked 12-3 | 26' truck - DC Electrician will show up at 1 to connect
|  | 1:00-6:00 pm | Lay wood as per supplied drawing, tape, lay carpet
|  | 16:00 | field set up FTA/FS (6 helpers). Confirmed for James Cerar (2020)
|  | 18:00 | AV Contractors truck arrives for unloading | 2 |  |  | 26'
|  | 18:00 | Dinner fieldside (delivery) |  | TBD
|  | 19:30 | Leave building unless key role personnel are in attendance | 6
Security | NA - venue locked |  | Security - main gym only - security not needed if venue locked
Day 0, February 28, 2020 | Day 0 - DAY 0 | 7:00 am | FIRST staff and EM | 2 FIRST, and EM, EMA | 4
EMT. 2:30-8pm | 2:30PM-9:00PM | 8:00 am | FTA/FS, AV Contractors crew set up | 6-8 helpers for field set up | 16
Machine Shop | 4:00PM-8:00PM | 8:00 am | Breakfast on table field side - working breakfast | 15 people | 20
|  | 12:00 pm | Lunch | 35 | 35
|  | 2:00 pm | Load-in Coordinator prepares for team Load-in, organizes Team package distribution | 4
|  | 3:00-5:00 pm | Team LOAD-IN | 4 |  |  | 40 vehicles - truck/trailers
|  | 5:00 pm | Dinner - grab and go (inspectors eat at 4:30PM) |  | 72+3/22
|  | 5:00 pm | PITS OPEN
|  | 5:30-7:30pm | Practice match filler line only *have CSA ensure all robots have connected to field |  |  | only if field ready
|  | 6:30 pm | Judges dinner |  | 22
|  | 7:45pm | EM to inform all key role staff of 7:30am SHARP meeting, and end of day upates
|  | 8:00 pm | PITS CLOSE
Security | 7:45PM-6:45AM |  | Security
Day 1, February 29, 2020 | Day 1 - DAY 1 | 6:45 | FIRST STAFF ARRIVE, EM, EMA | 5
EMT | 7:00AM-8:00PM | 7:00 | BREAKFAST FOR VOLUNTEERS and JUDGES |  | 70+3/22
Machine Shop | 8:00AM-7:00PM | 7:30 | Key Role Event Meeting - IMPORTANT - only KRL's | 12
|  | 8:00 | PITS OPEN |  |  | any FINAL TEAMS Load-in?
|  | 9:00 | Drivers Meeting
|  | 9:30 | Practice Matches
|  | 11:00 | OPENING CEREMONIES
Guest Speaker - Don Lovisa, President, Durham College
Guest Speaker - John Henry, Durham Regional Chair & CEO
Guest Speaker - Caitlin Dwight, Innovation Specialist, Ontario Power Generation
|  | 11:30 | Qualification Matches
|  | 13:30 | LUNCH BEGINS |  | 75+3/22
|  | 14:30 | Qualification Matches
|  | 18:00 | VOLUNTEER Dinner provided - rotating shifts |  | 75+3
|  | 19:00 | MATCHES END *if running late inform teams 2.0- hours in advance
|  | 19:45 | EM to inform all key role staff of NO Day 2 meeting, but to remind KRL's to check in with FC Event Lead and/or EM by 7:45am Day 2
|  | 20:00 | PITS CLOSE
Security | 7:45PM-6:45AM |  | Security
Day 2, March 1, 2020 | Day 2 - DAY 2 | 6:45 am | FIRST STAFF ARRIVE, EM, EMA | 104
EMT | 7:00AM-8:00PM | 7:00 am | BREAKFAST FOR VOLUNTEERS |  | 70+3/22
Machine Shop | 8:00AM-4:00PM | 7:45 am | Key Role Leads to check in with FC lead and/or EM | 12
|  | 8:00 am | PITS OPEN | 104
|  | 9:00 am | OPENING CEREMONIES
Guest Speaker, Dan Carter, Mayor of Oshawa
Guest Speaker, Ryan Werenich, Operations Manager GTA East Operations - Area 40, Enbridge
|  | 9:30 am | MATCHES BEGIN
|  | 9:30 am | Rookie plaques prepared and brought to FMS
|  | 1:00 pm | ALLIANCE SELECTIONS
Rookie plaques, speakers
|  | 1:30 pm | LUNCH BEGINS - Ri3D presentation at lunch |  | 75+3/22
|  | 2:30 pm | ELIMINATION ROUNDS BEGIN
|  | 5:30 pm | AWARDS
Guest Speaker?
|  | 7:30 pm | PITS CLOSE
|  | 6:30-9:00 pm | Electric Contractors take down
|  | 8:00 pm | Pizza Dinner fieldside for tear down crew |  | 35
|  | 9:00 pm | AV Truck loads up, teams leave | 104
|  | 9:30 pm | FIRST Transport loads up
|  | 10:30 pm | Building cleared

## Carleton 2020 Detailed Schedule (hidden)
Venue District Event (active document changing overtime) | [6 empty] | Follow Up Items
| 26 Teams | 10 Min. Cycle Times | Qualification Matches = 9 hours
Date | Day | TIME | Comments | # Vol's req'd | FOOD COUNT | Dock | Actions:
Note - confirm FIRST access time = flooring previously laid to accommodate
Day -1 | Day -1 Mar 12 |  |  | 1
|  | 0.25 | Athletics Staff to lay vinyl floor cover - Bleachers out before the Start of laying plastic flooring | 1
|  | 0.375 | FIRST staff lead arrives (likely 10am), FIRST Senior Mentor assistance
|  | 0.41667 | assign key vol's (Anthony) to review plan for Parking to go over the truck routes, timing |  |  |  | Forklift Onsite 9:30AM - 12PM
|  | 0.4375 | Venue set up crew (bring 10-12 people) to set up plastic/rubber Event Flooring (Rental Company has requested 10-15 people to assist with Unloading and Setup) | 10
|  | asap | Pit layout - need 3 volunteers - and set up tables, team number signs, tape pit locations, flooring / field layout / AV allows electrical power installation for pits | 4
|  | 0.52083 | Fieldside Lunch (Sandwiches), served in Volunteer Lounge |  | 15-20
|  | 0.5625 | Add floor underlay (wood if needed) *FC wood not needed, only MS
| Carleton preferred access times for 53' truck | 0.66667 | FIRST Truck unload - john contact, no alex, joel will be there | 6 |  |  | Forklift Onsite 2PM - 4PM
|  | 0.70833 | Electric Contractors (carpet and electrical work) • Pit electricity to be laid, cable mats, wheel chair mats to be installed • Carpet rolled, taped, vacuumed
|  | 0.72917 | Fieldside Dinner (Pizza), served in Volunteer Lounge |  | 15-20
| *only where room access available | 2:00 pm - 6:00 pm | (complete what tasks can be done at this time) • Field perimeter road cases positioned - Day 0 am • Volunteer Lounge, Committee room - thurs ampm, • Judges room – meeting rooms - Day 1 morning, Day 0 at Bakers Rest. • Chairman’s Award interview – room # - set up thurs/fri • Dean’s List – room # - same • VIP space set up - all event • Set up SWAG - thurs/fri - what suits FC
NOTE - what items from previous line is not completed, it is done on Day 0
Prayer Room - Setup not required, Quiet Room - becomes available 7PM Day 0
| *if space is available | 0.75 | Pits to be completed (pit admin, signs, inspection, magna roll out banner)
|  | *6:00 pm | Deans List, Chairmans Interview Room, FIRST Staff/Safety Advisor Room set up to be completed
AV Contractors truck arrives to unload and go
|  | 0.85417 | clear building
Security |  | 8:00 pm - 7:00 am | Overnight Security on-site (Student Safety Patrollers)
Day 0 | Day 0 Mar 13
|  | 0.28125 | FIRST Staff and Key CU personnel arrive on-site
|  | 0.29167 | FED Event Staff arrive on-site (Anthony, Alex L, Laura, Jennifer)
|  | 0.33333 | Breakfast (served in Volunteer Lounge) |  | 25
Setup crew Volunteers arrive on-site (FTA/CSA/Pit Admin...)
Auxillary Rooms setup as they become available (First Aid, VIP Lounge, etc.)
| *might be done thurs |  | *FIRST Merch and Carleton Recruitment booths setup
|  | ? | help needed to set up Generator on game field | 10
|  | 0.41667 | Scripts to be reviewed with EM
Elevator to Alumni Hall 2nd Floor unlocked and entered into service
|  | 0.5 | Lunch (served in Volunteer Lounge) |  | 40
|  | 0.54167 | Pits and Practice Field set up completed
|  | 1:30 pm - 5:30 pm | Student Safety Patrollers on-site to assist with Load-in and Traffic Control
connect wit Load-in coordinator - LRI
|  | 0.5625 | Meet with Parking Attendants to go over the Load-in for team arrival at 3pm
|  | 0.58333 | Safety/Emergency Preparedness Venue Walkthrough and Certification
| booths | 2:00 pm - 5:00 pm | Engineering & Science Recruitment teams on-site in Alumni Hall Concourse
EMT |  | 3:00 pm - 8:00 pm | Emergency Response Team (CUSERT) on-site, staffing First Aid Room
|  | 0.61458 | Load-in Coordinator to prep. for team Load-in - usually LRI
|  | 3:00 pm - 5:00 pm | TEAM LOAD-IN (One Hour per Team for setup - 5 wrist bands / team)
|  | 0.66667 | DJ, Carleton Student Clubs, Event Sponsors arrive for Team Social setup
|  | 0.6875 | Inspectors have dinner early to be ready to start robot inspection
EM to connect JA and Safety Managers when they arrive
|  | 0.70833 | Dinner (served in Volunteer Lounge, rotating breaks for Volunteers) |  | 65
Pit Admin may need food brought to Pit Admin table in pits
PITS OPEN
|  | 5:00 pm - 8:00 pm | TEAM SOCIAL (Norm Fenn Gym)
|  | 5:30 pm - 7:30 pm | Possible PRACTICE MATCHES
Judges Welcome Dinner & Orientation at Bakers Restaurant (University Centre bldg)
|  | 0.79167 | Quiet Room becomes available, setup begins
|  | 18:00 | Judges arrive - meeting 6-9pm
|  | 18:30 | Judges dinner served at Bakers Restaurant (University Centre bldg) |  | 24
|  | 19:30 | Matches completed, field preparation, end time dependent on FTA
|  | 19:45 | overnight requirement, EM informs Key Vol of 7:30am SHARP next day meeting in event office
|  | 0.83333 | PITS CLOSE
Security |  | 8:00 pm - 7:00 am | Overnight Security on-site (Student Safety Patrollers)
Day 1 | Day 1 Mar 14
|  | 0.25 | FED Event Staff arrive on-site (Anthony, Alex L, Laura, Jennifer)
Judges Lounge setup
|  | 6:45 | FIRST STAFF ARRIVE, Event Managers
|  | 7:00 | BREAKFAST (served in Volunteer Lounge & Judges Lounge) |  | 105
Convert Norm Fenn Gym from Social to Team Lounge
|  | 7:30 | Key role meeting - location TBD
Chairman's & Dean's List Interview Rooms setup
Carleton Recuritment Booths Open
|  | 8:00 | PITS OPEN
EMT (8:00AM-8:00PM) |  | 8:00 am | Emergency Response Team (CUSERT) on-site, staffing First Aid Room
Team Lounge Opens
Quiet Room Opens
|  | 9:00am | Drivers Meeting on main field
|  | 9:30am | Practice Matches (9:30-10:45am)
|  | 0.45833 | OPENING CEREMONIES
Benoit-Antoine Bacon, Carleton University President and Vice-Chancellor
Dave Ibbetson Vice President and General Manager, General Dynamics Mission Systems (exclusive presenting sponsor)
Grant Courville, Vice President, Products and Strategy, Blackberry QNX (pit sponsor)
|  | 0.47917 | QUALIFICATION MATCHES BEGIN
|  | 1:30 pm - 2:30 pm | Lunch (served in Volunteer Lounge & Judges Lounge) |  | 105
|  | 0.60417 | MATCH PLAY RESUMES (2:30-7:00pm)
|  | 17:30 | Dinner (ensure easy access for field crews working - have 8-10 boxed dinner containers available, in case of running late)
|  | 19:45 | EM advises key role volunteers about NO 7:30am SHARP morning meeting, but KRL's to report in to FC lead
Security 7:45-6:30am |  | 19:45 | Security arrives Overnight Security on-site (Student Safety Patrollers)
|  | 0.83333 | PITS CLOSE
Team Lounge Closes
Quiet Room Closes
Day 2 | Day 2 Mar 15
|  | 6:45 | FIRST STAFF and FED Event Staff (Anthony, Alex L, Laura, Jennifer) arrive on-site |  | 105
|  | 7:00 | Breakfast (served in Volunteer Lounge & Judges Lounge)
|  | 7:30 | NO Key role meeting - KRL's report to FC lead for check in
EMT 8am-6pm |  | 8:00 am | Athletic Therapy on-site, staffing First Aid Room
|  | 0.33333 | PITS OPEN
Team Lounge Opens
Quiet Room Opens
|  | 0.375 | OPENING CEREMONIES
Enbridge confirmed as per FIRST
|  | 0.39583 | MATCHES BEGIN (9:30-11:30am)
|  | 0.45833 | EM to bring Rookie Team plaques to the FMS table to present at start of Alliance Selections
|  | 0.47917 | ALLIANCE SELECTIONS
|  | 0.5 | LUNCH BEGINS (Takeout Containers will be available) |  | 105
|  | 0.54167 | ELIMINATION ROUNDS BEGIN (3 HOURS)
|  | 15:30 | judges (refresh beverages and light food)
|  | 0.66667 | AWARDS (4-5:30pm)
Pooja Suresh, Manager, Research and Innovation, Gastops, Carleton Engineering Alumna (confirmed)
|  | 0.75 | PITS CLOSE
Team Lounge Closes
Quiet Room Closes
|  | 0.72917 | Electric Contractors tear down and truck loads up | 4
|  | 0.75 | A/V crew tear down, truck load
|  | 19:00 | 10 needed to take down the generator | 10
|  | 19:00 | Dinner for tear down crews |  | 25
|  | 19:30 | Electric Contractors truck loads up
|  | 20:30 | AV Truck loads up |  |  |  | Forklift Onsite 8PM - 12AM
|  | 0.875 | FIRST Transport loads up | 8
|  |  | Event Flooring tear down, Madali Trasport loads up | 10
|  | 0.95833 | Building cleared
|  |  | *carpet taken away by FRC Team 2994 | 8 |  |  | 8 team members needed
Questions

## McMaster 2020 Detailed Schedule (hidden)
MCMASTER SCHEDULE APRIL 3-5 2020 (Day 0/Day 1/Day 2)
|  |  | 40 Teams Participating |  |  | GREEN means all set and confirmed
Date | Day | TIME | Comments | Vol's | FOOD Count | *new column to verify task completion | Details
2020-04-03 | Day 0 Day 0 | 5:45 | Set up crew and FIRST prepare for transport unloading Fork Lift arrival confirmed |  |  | TJ confirmed building access at 6am and hallways cleared for Load-in | 53' transport truck
|  |  | note - 6am Load-in requires extra volunteers (6)to help all trucks unload and move equipment from unloading area and into main gym and all the way to the pit gym | 2020-12-08
|  | 6:00 | Mac team sets up pits, rooms where available | 10
|  | 6:15 | FIRST 53' transport arrives to unload |  |  | Vol's to be there to be ready to unload truck - Melissa/Michael confirming 4039 members
|  | 6:30 | Electric Contractors Truck 26' & carpet arrival | 4 |  | Electric Contractors confirmed arrival time
|  | 7:30 | GRAB truck 26' arrives to unload
|  | 7:45 | Continue - SET UP - AV, wood/carpet/field layed, all ancillary rooms, pits |  |  | lead EMT? | 26' truck AV
|  | 7:45 | Breakfast snack fieldside |  | 18 | Arlene Dosen - Larry Marsh -> 20 volunteers
|  | 12:00 | Lunch - field side |  | 30
|  | 2:15pm | Load-in Coordinator (LRI) | 4+2 |  | prepares for teams to Load-in, 4 inside, 2 outside
can we get extra help with outside Load-in management
EMT | 2:30PM-9PM | 2:30 - 5:00 pm | Team LOAD-IN - 5 team members, 1 hour only |  |  |  | 40 vehicles - truck/trailers
|  | 16:30 | Inspector Dinner - rotating so as to monitor Load-in of teams |  | inspectors eat 4:30-5pm
|  | 5:00pm | Pits Open and Inspection
|  | 5:30pm | Team filler line matches until 7:30pm, robot calibration |  | 60 | volunteer lounge / compare food count to 2019 #'s
|  | 5:30-7:30pm | Practice filler line - only for inspected robots
|  | 5:30-7:30PM | Matches completed, field preparation, end time dependent on FTA |  |  | Team Social Mezzanine, Ivor Wynne Centre - pizza!
|  | 18:00 | Judges arrive - meeting 6-9pm
|  | 18:30 | judges dinner served
|  | 7:45pm | EM informs Key Vol of 7:30am SHARP next day
|  | 8:00pm | PITS CLOSE
Security | 8:45PM-7:00AM |  | Security
2020-04-04 | Day 1 Day 1
|  | 6:45 | FIRST STAFF ARRIVE, SHOW READY
EMT | 8:00AM-8:00PM | 7:00 | BREAKFAST FOR VOLUNTEERS
|  | 7:30 | Key Role staff Meeting - event office
|  | 8:00 | PITS OPEN
|  | 9:00 | Drivers meeting on field
|  | 9:30 | Practice Matches (9:30-10:45am)
|  | 11:00 | OPENING CEREMONIES
|  | 11:30 | Qualification Matches
|  | 13:30 | LUNCH BEGINS - Dean's List Luncheon |  |  | VIP Lounge - Ivor Wynne Centre - Mezzanine
|  | 14:30 | Qualification MATCHES (2:30-7pm)
|  | 17:30 | Dinner (ensure easy access for field crews working - have 8-10 boxed dinner containers available, in case of running late) |  |  |  | grab and go snack
|  | 19:00 | MATCHES END
|  | 19:45 | EM advises key role volunteers about 7:30am SHARP morning meeting
|  | 19:45 | Security arrives - is security needed or space lockedown?
Security | 7:45PM-7:00AM | 20:00 | PITS CLOSE
2020-04-05 | Day 2 Day 2
|  | 18:45 | FIRST STAFF ARRIVE, EM & EMA
EMT | 8:00AM-7:30PM | 7:00 | BREAKFAST FOR VOLUNTEERS
|  | 7:30 | NO Key role meeting - KRL's report to FC lead for check in
|  | 8:00 | PITS OPEN
|  | 9:00 | OPENING CEREMONIES
Mark Egbedeyi-Emmanuel (also judging) - Union Gas
|  | 9:30 | MATCHES BEGIN
|  | 1:00 | ALLIANCE SELECTIONS
|  | 13:30 | LUNCH BEGINS
|  | 14:30 | ELIMINATION ROUNDS BEGIN
|  | 17:30 | AWARDS
|  | 19:30 | PITS CLOSE
|  | 19:30 | Electric Contractors and GRAB take down
|  | 20:00 | Forklift required to stack and load road cases
|  | 21:00 | AV Contractors, Electric Contractors Truck loads up, teams leave
|  | 21:30 | FIRST Transport loads up
|  | 22:30 | Building cleared

## Georgian 2020 Detailed Scehdule (hidden)
| 28 Teams | 9.0 Min. Cycle Times | Qualification Matches = 12 hours
Requires response by John H.
Requires response by Georgian
Date | Day -1 | TIME | Comments | #Vol's Req'd | Food Count | Dock | Details
|  | 15:00 | FC to arrive to Georgian for planning with Mark
*early access allows electrical early set up
| LE tie in early | 3pm/4pm | meet with the onsite electrician around 3/4pm, then they go get a bit to eat, and then come back at 6:30pm to set up. Make sense
2020-03-05 | Day -1 | 6-10pm | Can Georgian get 6 people to help Vynal flooring completed by 6pm | 6-8 vol's
|  | 18:00 | Set up crew - FIRST (2+?)
|  | 16:00 | Mark on the floow PIT drawings
|  | 18:00 | FIRST Truck unloads +2 Georgian staff, 2 - 4 additioinal helpers | 6-8 for FIRST truck |  | forklift 6-9pm | FIRST 53' transport
|  | 18:30 | *need pit layout set up for electrical placement
|  | 19:00 | Electric Contractors Arrives with carpet *unroll carpet asap (may unload early if bleachers are set up) | 4 assist with carpet |  |  | Electric Contractors 26' truck
|  | 19:30 | dinner snack on table in field area (sandwiches)
|  | 20:00 | AV Contractors truck arrives to unload - no set up |  |  |  | GRAB 26' truck
Room Setup's - who?, pit set up marking pits for electrical, practice field, pit admin
|  | 22:00 | clear building
Security (9:30PM-7:00AM) |  |  | *security needed - yes or full facility lock down?
2020-03-06 | Day 0 Day 0 | 7:00 | FIRST and Georgain representatives arrive
|  | 7:30 | Set Up crew
|  | 8:00 | AV Contractors, FTA and FS crew arrives | FTA/FS + 8 |  |  | 7:00am - 8 Georgian oganised vol's specifically for set up work
|  | 8:00 | light Breakfast snack fieldside
|  | 12:00 | Lunch field side to promote continuous working |  | 35
EMT (3:00-8PM) |  | 3:00 - 5:00 PM | Team LOAD-IN & PITS OPEN - *Teams welcomed, staff visiting vehicles to greet teams, onsite activities, flyers | 4 assist with Load-in
|  | 16:30 | Inspector Dinner - rotating so as to monitor Load-in of teams |  |  | inspectors eat 4:30-5pm
|  | 17:00 | Volunteer Dinner
|  | 17:00 | Pits Open and Inspection
|  | 17:30 | Team filler line matches until 7:30pm, robot calibration
|  | 18:00 | Judges arrive - meeting 6-9pm
|  | 18:30 | judges dinner served
|  | 19:30 | Matches completed, field preparation, end time dependent on FTA
Security (7:45PM-6:45AM) |  | 19:45 | overnight requirement, EM informs Key Vol of 7:30am SHARP next day meeting in event office
|  | 20:00 | PITS CLOSE
2020-03-07 | Day 1 Day 1 | 6:45 | FIRST STAFF ARRIVE, Event Managers
EMT (8:00AM-8:00PM) |  | 7:00 | BREAKFAST FOR VOLUNTEERS |  |  |  | 80% will attend
|  | 7:30 | Key role meeting
|  | 8:00 | PITS OPEN |  |  | FINAL TEAMS Load-in
|  | 9:00 | Drivers Meeting on main field
|  | 9:30 | Practice Matches (9:30-10:45am)
|  | 11:00 | OPENING CEREMONIES
speakers
speakers
speakers
|  | 11:30 | MATCHES BEGIN
|  | 13:30 | LUNCH BEGINS
|  | 2:30pm | MATCH PLAY RESUMES (2:30-7:00pm)
|  | 17:30 | Dinner (ensure easy access for field crews working - have 8-10 boxed dinner containers available, in case of running late)
|  | 19:45 | EM advises key role volunteers about NO 7:30am SHARP morning meeting, but KRL's to report in to FC lead | see rollout
Security (7:45PM-7:00AM) |  | 19:45 | Security arrives
|  | 20:00 | PITS CLOSE
2020-03-08 | Day 2 Day 2 | 6:45 | FIRST STAFF ARRIVE, SHOW READY
EMT (8:00AM-6:00PM) |  | 7:00 | BREAKFAST FOR VOLUNTEERS
|  | 7:30 | NO Key role meeting - KRL's report to FC lead for check in
|  | 8:00 | PITS OPEN
|  | 9:00 | OPENING CEREMONIES
Enbridge - FC sponsor
speakers
speakers
|  | 09:30:00 | MATCHES BEGIN (9:30-11:30am)
|  | 10:30 | judges (refresh beverages and light food)
|  | 11:30 | ALLIANCE SELECTIONS
|  | 12:00 | LUNCH BEGINS
|  | 13:00 | ELIMINATION ROUNDS BEGIN (3 HOURS)
|  | 15:30 | judges (refresh beverages and light food)
|  | 16:00 | AWARDS (4-5:30pm)
|  | 18:00 | PITS CLOSE
|  | 17:30 | Electric Contractors arrives to start tear down, truck loads up | Georgian Electrician can disconnect on Monday - Arti/Kirsten to coordinate
|  | 18:00 | AV Truck tear down begins, loads up
Fork Lift - 8pm |  | 19:30 | Electric Contractors truck loads up |  |  | Fork Lift - 8pm
|  | 20:30 | AV Truck loads up
|  | 21:30 | FIRST Transport loads up
|  | 22:30 | Building cleared
3.0 hours of Elemination rounds - quarter/semi/finals

## York 2019 Detailed Schedule (hidden)
York Schedule 2019
36 Teams, 7 min. match cycle times
Date | Day | TIME | Comments | # of VOLUNTEERS | Dock | Details | Actions
2019-03-21 | Day -1 Day -1 | 15:00 | Floor Coverings by York in PIT gym
|  | 15:00 | FIRST staff arrive
|  | 15:00 | This means taping the floor for pit locations, identifying practice field location. and having pit drawing available for Litte Electric - Large measuring tape, chalkline, white tape (gaffers tape), marker | 4 volunteers to set up
Forklift required (4:00-8:00 pm) |  | 4:00 pm | Electric Contractors - carpet and electric work (Volunteers to help with Carpet - any forklift requirements?) | 4 to help unload carpet | Forklift | 26' truck
|  | 5:00 pm | FIRST 53" transport truck arrives - *forklift required
Truck Offloaded and roadcases on side
Get access to roadcase 8 and move roadcases to appropriate areas (side)
|  | 18:00 | Phil to add the number of volunteers here
|  | 18:00 | Pit layouts required to be complete
• Pit electricity to be laid, cable mats, wheel chair mats to be installed • Pit tables and team pits to be ready • Pit Admin road cases to be ready • Carpet rolled, taped, vacuumed • Field perimeter positioned, connected • Volunteer Lounge, Committee room, Mentor Lounge set up • Judges room – meeting rooms • Chairman’s Award interview – room # • Dean’s List – room # • VIP space set up • Set up SWAG Tables
|  | 18:00 | Lay wood as per supplied drawing, tape, lay carpet (check with FTA/FS)
|  | 18:00 | field set up FTA/FS (6 helpers). OPTIONAL for FTA/FS
|  | 18:30 | AV Contractors unload and hold
|  | 20:00 | PIT's to be fully ready, carpet to be rolled out, roadcases in the right areas
|  | 20:00 | Rooms should have furniture and road cases
SECURITY | 8:45PM-6:45AM | 20:00 | Leave building unless key role personnel are in attendance Security to sit between main gym and fieldhouse (pits)
2019-03-22 | Day 0 Day 0 | 6:45 am | FIRST staff and EM Arrive
EMT | 2:30PM-9:00PM | 7:30 | FTA/FS, AV Contractors Crew set up
Field Setup and Event set up continues - Main feild setup - PIT setp (PIT Admin, ensure viewing area is clear, pipe and drape is done, Machine shop area is clear, practice area is pipe and draped) - Create walkway for teams in/out of the main field + pipe and drape or extensions to divide group - Signage and directional signage - Judges rooms, Volunteers rooms and Interview rooms - Corridor free of hazards / safety check - Load-in Area defined and clear
|  | 7:30 | Phil to add the number of volunteers here
|  | 8:00 am | Breakfast
|  | 12:00 | Lunch
|  | 1:30 pm | Event should be fully ready incl. pipe and drape across all areas
|  | 14:30 | Venue should be event ready. EM and FC Staff to ensure Load-in area is set up and clear. volunteers assigned to sign off as teams come in. PIT Admin Volunteer onsite
|  | 2:30 - 4:30 pm | Team LOAD-IN & PITS OPEN
|  | 16:30 | Pits Open and Inspection
|  | 17:00 | Dinner |  | 27
|  | 5:30 - 8:00 pm | PRACTICE MATCHES / Robot Calibration
|  | 20:45 | EM advises key role volunteers about 7:30am SHARP morning meeting
|  | 21:00 | PITS CLOSE
SECURITY | 8:45PM-6:45AM | 20:45 | overnight requirement
2019-03-23 | Day 1 Day 1 | 6:45 | FIRST STAFF ARRIVE, EM and Venue Representative
EMT | 7:00AM-8:00PM | 7:00 | BREAKFAST FOR VOLUNTEERS | 90 | 27 |  |  | 75
|  | 7:30 | Key Role meeting |  |  | 50 |  | 14
|  | 8:00 | Pits open
|  | 8:00 am | EM to remind PIT announcer to make announcements of Drivers meeting at 8:30am on main field
|  | 8:30 | Drivers meeting on game field
|  | 9:15 am | Practice Matches |  |  |  |  | 10
|  | 10:30 | Judges replinshment + mentors lounge snack
|  | 10:45 am | Practice Matches End
|  | 11:00 | OPENING CEREMONIES
|  | 11:30 | MATCHES BEGIN (2.5 hours)
|  | 13:30 | LUNCH BEGINS | 97 | 27 |  | 15
|  | 14:30 | MATCH PLAY RESUMES (2-5:30) (3.5 hours)
|  | 15:30 | Judges replinshment + mentors lounge snack
|  | 18:00 | Dinner | 92 | 27
|  | 19:00 | Qualifications Matches End
|  | 19:45 | EM advises key role volunteers about 7:30am SHARP morning meeting
SECURITY | 7:45PM-6:45AM | 20:00 | PITS CLOSE
2019-03-24 | Day 2 Day 2 | 6:45 am | FIRST STAFF ARRIVE
EMT | 7:00AM-8:00PM | 7:00 | BREAKFAST FOR VOLUNTEERS | 90 | 27
|  | 8:00 | PITS OPEN
|  | 9:00 | OPENING CEREMONIES
|  | 9:30 | MATCHES BEGIN (3.0 hours)
|  | 10:30 | Judges replinshment + mentors lounge snack
|  | 13:00 | ALLIANCE SELECTIONS
|  | 13:30 | LUNCH BEGINS | 97 | 27 |  | 15
|  | 14:30 | ELIMINATION ROUNDS BEGIN (3 HOURS)
|  | 15:30 | Judges replinshment + mentors lounge snack |  | 27 | 30
|  | 17:30 | AWARDS
|  | 19:30 | PITS CLOSE
|  | 19:00 | Electrical tear down starts in pits
|  | 19:00 | Pipe and drape tear down begins in pits
|  | 19:30 | AV tear down begins
|  | 21:00 | AV Truck loads up
|  | 21:00 | Electrical truck loads up
|  | 21:30 | FIRST Transport loads up | 30
|  | 22:30 | Building cleared

## Ryerson 2020 Detailed Schedule (hidden)
RYERSON District Event | [6 empty] | Follow Up Items
| 30 Teams | 8.0 Min. Cycle Times | Qualification Matches = 12 hours |  |  |  | - john to confirm with Emily about steel chairs around south end of rink
- John to seek redraw with field perimeter
Blue - confirmed status |  |  | WEEK 3
Orange = Commited, not yet in VMS |  |  | March 12 - 14, 2020
Green = Assigned in VMS |  |  | RYERSON UNIVERSITY
Event Special NOTES... |  |  | 30 teams
Date | Day | TIME | Comments | # Vol's required | Food | Dock | Actions: | Questions for Emily | Details | Food Service
|  |  | Humber truck to Ryerson | [6 empty] | Vol's | Judges | Mentors | VIPS | Total |  | Elevator ACcess
2020-03-11 | Wednesday | 8:00 | FIRST staff | 2+ | 6 |  | arti, john, paul, kim, ? |  | field set up, unload truck, unroll carpet
Ryerson Floor will be ready by ?
|  | 8:00 am - 4:00 pm | Stage Vision (they bring 4 people) ( elevator access required) (they leave at 3ish) | 0 | 4 | no forklift required | Need Ryerson Drawings (John), No forklift needed | stage vision in contact and Union will be there | [7 empty] | Elevator Access: 7:30 AM - 2:00 PM
|  | 9:00 | Hahn (PIT set up and lower level rooms set up, pipe and drape) | 0 |  |  | Hahn will layout pits & chalk them etc. (John to PIT Map/drawing) Arti to provide Spec Sheet (Rooms set up etc,)
Confirm Internet connections with Emily
|  | 8:30 | Electric Contractors (carpet and electrical work)
Arti to meet with Emily/IT followed by Parking (Sam)
|  | 10:00 | FIRST Truck unloads | 6 |  | yes Forklift |  |  | No union required
Check with Jonathan if he has volunteers
|  | 11:00 | Phil's Truck (trailer: 5 items: machine shop, 5 roadcases - Sponsor+Consumables +webcast)
|  | 11:00 - 12:30 PM | Roadcases in the areas
Ground Level : 2 Banners
Set up VIP Registration desk (table cloth/banners)
|  |  | VIP Lounge (TV, vases, brochuers), banners, | make sure white cloth are done
Chairmans, Dean's List Room (8ft drape) + table skirt
Set up PIT Admin (Safety Glasses, Spare parts and Machine Shop, Practice Field) ----- 1/2 hr
Magna Banner set up
|  | 12:30 -12:45 | Lunch (room) |  | 10 | [8 empty] | 0
|  | 1:00 PM- 2:30 PM | Magna Banner Roll out (require 4 volunteers)
PIT Set up (Magna table cloth on PIT Admin desks, Magna "PIT Sponsor" bannersin PITs
Judges Rooms, Event Office Set up
VIP Room Set up (banners, TV, USB, Podium, Riser, EAB Meeting Setup)
Volunteer Lounge to be
|  | 2:00 - 5:00 pm | • Pit electricity to be laid, cable mats, wheel chair mats to be installed • Carpet rolled, taped, vacuumed • Field perimeter positioned, connected (Only if PT wants to set up these rooms on Thurs or Fri?) |  |  |  | • who is required • who is required • who is required • who is required • who is required • who is required
|  | 17:00 | Pits to be completed (pit admin, signs, inspection, magna roll out banner) |  |  |  |  | ACCESS to the Buidling (until 10pm)? FIRST will provide details in 24 hrs
| maybe | 6:00 pm | Deans List, Chairmans Interview Room, FIRST Staff/Safety Advisor Room set up to be completed |  |  |  |  | Do we have access to rooms on Wed
|  | 18:00 | FTA/FS arrive field set up |  |  |  | when is FTA arrival
|  | 18:30 | dinner staff, AV, others? union?
|  | 18:00 | Field Set up
|  | 21:00 | clear building |  |  |  |  | Check with Emily if we have the building till 10pm
Security | 8:45PM-7:45AM |  | Night Security???
2020-03-12 | Day -1 | 7:45 | FIRST key people |  |  | yes - 1 hour
EMT | 1:30PM-9:00PM | 8:00 | Set up crew volunteers (FTA/CSA/PITAdmin...) breakfast | [10 empty] | 0
|  | 8:00 | Breakfast
|  | 11:00 | Meet with Parking Attendant to go over the Load-in and Load-out
|  | 12:00 | Lunch | [10 empty] | 0
|  | 1:00 pm | PITs and Practice Field set up
|  | 2:00 pm - 9:00 pm | Stage Vision Arrives
|  | 1:30 pm - 4:30 pm | Team LOAD-IN (one hour team pit set up) * elevator available 2-10PM |  |  |  |  | Change the request to Emily to move itming to 8PM instead of 7 PM | 40 vehicles - truck/trailers
|  | 16:30 | PITS OPEN | [11 empty] | *judges dinner to be in judges room
|  | 5:00 pm | Rotating DINNER (Judges will also have dinner - Ryerson) -confirm timing with John Smith
|  | 5:30 pm - 8:00 pm | FILLER LINE PRACTICE MATCHES
|  | 20:45 | EM informs Key volunteers to attend 7:30am next day meeting
|  | 21:00 | PITS CLOSE | [5 empty] | *no team Load-in after 8pm
Security | 8:45PM-7:15AM |  | Night Security
2020-03-13 | Day 0 | 6:45 | FIRST STAFF ARRIVE
EMT | 8:00AM - 8:00PM | 7:00 | BREAKFAST FOR VOLUNTEERS | [5 empty] | 80% will attend
|  | 8:00 | PITS OPEN |  |  | FINAL TEAMS Load-in
|  | 8:30 | DRIVERS MEETING (on field)
|  | 9:15 | PRACTICE MATCHES
|  | 11:00 | OPENING CEREMONIES
|  | 11:00 | GUEST SPEAKER (Ryerson, Scotiabank, Magna (Award)
|  | 11:30 | QUALIFICATION MATCHES | [5 empty] | 2.5 hours of match play
|  | 13:30 | LUNCH BEGINS
|  | 2:30 pm - 7:00 pm | QUALIFICATION MATCHES | [5 empty] | 4.5 hours of match play
|  | 19:45 | EM informs Key volunteers to attend 7:30am next day meeting
|  | 20:00 | PITS CLOSE
Security | 7:45PM-7:15 AM |  | Night Security
2020-03-14 | Day 1 | 6:45 | FIRST STAFF ARRIVE
EMT | 8:00AM-7:30PM | 7:00 | BREAKFAST FOR VOLUNTEERS
|  | 8:00 | PITS OPEN
|  | 9:00 | OPENING CEREMONIES
|  | 9:30 | QUALIFICATION MATCHES | [5 empty] | 3.5 hours of match play = 10.5 total qualification rounds
|  | 13:00 | ALLIANCE SELECTIONS
|  | 13:30 | LUNCH BEGINS
|  | 14:30 | ELIMINATION ROUNDS BEGIN | [5 empty] | 3.0 hours of Elemination rounds - quarter/semi/finals
|  | 15:00 | Close out CanCode
VIP Lounge
VIP Desk can be cleaned out
SWAG -
FLL
|  | 17:30 | AWARDS
|  | 19:30 | PITS CLOSE
Forklift req'd 8-11pm |  | 7:00 - 9:00 pm | Hahn (Truck has to leave dock by 8:30 pm) *this cannot be confirmed!
|  | 8:00 (truck: 8:30 - 9:00 pm) | Electric Contractors
|  | 9:30 - 10:00 pm | AV Truck loads up
|  | 22:30 | Building cleared
2020-03-15 | Day 2 | 10:00 am - 1:00 pm | FIRST Truck Load