## Sheet1
Build Season Timeline
ACTIVITY | Week
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8+
Initial Strategy (~First 2-3 days) | bar: Week 1 to Week 2
Mechanism Brainstorming + Choosing prototype concepts (~2 days) | bar: Week 1 to Week 2
Prototyping | bar: Week 2 to Week 4
Detailed Design | bar: Week 2 to Week 4
Mechanism Fabrication | bar: Week 2 to Week 6
Assembly (includes wiring) | bar: Week 4 to Week 6
Initial Programming | bar: Week 2 to Week 6
Test and Finalize Programming | bar: Week 4 to Week 7
Practice/Testing | bar: Week 6 to Week 8+
Iterating | bar: Week 6 to Week 8+